## List
Latest update : 14-Jul-2023, Gabriel
|  | System | Scope | Category | Phase | Task | Note
|  | General | Inclusion | Service | Initialization | Introducing <system name>
|  |  | Assumption / Customer Responsibility | Service | Initialization | Attending project briefing
[5 empty] | Proposal | Conducting office based technical feasibility study for <project name>
[5 empty] | Proposal | Attending Site survey for <project name>
[5 empty] | Proposal | Arranging onsite test, trial or pilot
[5 empty] | Proposal | Attending onsite test, trial or pilot
[5 empty] | Proposal | Clarifying <system name> requirements
[5 empty] | Proposal | Drafting technical proposal for <project name>
[5 empty] | Proposal | Drafting high level project plan
[5 empty] | Proposal | Drafting project org-chart
[5 empty] | Proposal | Drafting scope of work (inclusion and exclusion) and customer responsibility or assumption
[5 empty] | Proposal | Providing supplied product <hardware or software> datasheet
[5 empty] | Proposal | Providing supplied product <hardware or software> certificate
[5 empty] | Proposal | Providing quotation
|  | General | Exclusion | Service |  | Anything that is not included in inclusion is considered out of scope.
[5 empty] | Design | Identifying <system name, e.g. MGC, CSMS, HEMS> requirement details
[5 empty] | Design | Identifying existing site condition (via conducting site survey or other method)
[5 empty] | Design | Assessing compliance and drafting compliance table according to <document, e.g. tender, RFP>
[5 empty] | Design | Drafting Architecture Diagram of <system name>
[5 empty] | Design | Drafting Network Connection Diagram of <system name>
[5 empty] | Design | Drafting Layout Diagram of <system name> control panel
[5 empty] | Design | Drafting Wiring Diagram of <system name> control panel
[5 empty] | Design | Producing BOQ / BOM of <system name>
x | x
|  | MGC | Assumption / Customer Responsibility | Service | Microgrid Design - Pre-Sales | Microgrid design to be provided by 3rd party and should be made available to LITEON with details as the principle of Microgrid controller's operation
|  | MGC | Exclusion | Service | Microgrid Design - Pre-Sales | Gathering necessary information required for designing and specifying high level Microgrid Design and consultation service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | Microgrid Design - Pre-Sales | Providing high level Microgrid Design and consultation service as well as implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | MGC | Exclusion | Service | Microgrid Design - Pre-Sales | Providing offer, including but not limited to : Microgrid Design and consultation service Feasibility Study Report, Microgrid System Architecture, Microgrid System Components, Conceptual Design Report, Project References, (Optional) Financial Models, details and cost of Microgrid Design and consultation service to be supplied in execution phase (e.g. System Design Documents, Microgrid System Component Technical Specifications, Control System Documentation, Integration Documentation, Commissioning and Acceptance Test Plans, Operations and Maintenance Documentation, Cybersecurity Documentation, Warranties and Life Cycle costs), project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning). More details refer to Sheet "MicrogridDesignDocs"
|  | MGC | Exclusion | Service | Microgrid Design - Pre-Sales | Evaluating and accepting Microgrid Design and consultation service offer (including commercial negotiation)
|  | MGC | Exclusion | Service | Microgrid Design - Execution | Gathering necessary information required for performing Microgrid Design and consultation service, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | Microgrid Design - Execution | Performing Microgrid Design and consultation service, providing System Design Documents, Microgrid System Component Technical Specifications (e.g. brand and model of DERs; Smart Electrical Distribution Board; Cables; other accessories and intended high level installation position and method), Control System Documentation, Integration Documentation, Commissioning and Acceptance Test Plans, Operations and Maintenance Documentation, Cybersecurity Documentation, Warranties and Life Cycle costs according to <document, e.g. design, proposal, tender>
|  | MGC | Exclusion | Service | Microgrid Design - Handover | Liaising with <certifying party, normally consultant from customer> to certify or endorse submitted Microgrid design
|  | MGC | Exclusion | Service | Microgrid Design - Handover | <Note : Microgrid designer task ends here. In normal case this role's scope is only performing Microgrid design but not taking care of the the project execution. The microgrid design certification party continuing in steering the execution as Consultant. However, it is possible that the certification party fades out and Microgrid designer continues as Consultant. In any case, the Consultant should be at least Consulted in each phase as he is Accountable for the performance of microgrid at the end of the project>
x | x
|  | MGC | Assumption / Customer Responsibility | Service | DER Supplier - Pre-Sales | All listed equipment, devices, components and 3rd party systems (Genset, BESS, PV, DB, UPS, Network Switch, PLC, SCADA etc.) are to be supplied, installed and commissioned by 3rd party, except suppling and commissioning Edge Advance (Microgrid Controller) to be done by LITEON
|  | MGC | Exclusion | Hardware | DER Supplier - Pre-Sales | Gathering necessary information required for designing and specifying DER component or system to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Hardware | DER Supplier - Pre-Sales | Designing and specifying <DERs, e.g. PV system, Genset, Wind Turbine system etc.> as well as drafting installation position and method according to <document, e.g. Microgrid design, proposal, tender>
|  | MGC | Exclusion | Hardware | DER Supplier - Pre-Sales | Providing offer, including but not limited to : DER component or system to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availbility, maintenance contract for supplied hardware.
|  | MGC | Exclusion | Hardware | DER Supplier - Pre-Sales | Evaluating and accepting DER supplying offer (including commercial negotiation)
|  | MGC | Exclusion | Hardware | DER Supplier - Execution | Gathering necessary information required for supplying DER, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Hardware | DER Supplier - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding DER installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | MGC | Exclusion | Hardware | DER Supplier - Execution | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Hardware | DER Supplier - Execution | Approving submitted DER supplying MoS
|  | MGC | Exclusion | Hardware | DER Supplier - Execution | Performing DER supplying tasks according to approved MoS
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Accepting completion report
|  | MGC | Exclusion | Hardware | DER Supplier - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Hardware | DER Supplier - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Hardware | DER Supplier - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Hardware | DER Supplier - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Hardware | DER Supplier - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Hardware | DER Supplier - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | DER Installer - Pre-Sales | Gathering necessary information required for installing supplied DER component or system, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | DER Installer - Pre-Sales | Liaising with <DERs, e.g. PV system, Genset, Wind Turbine system etc.> supplier to specify supplied <DERs, e.g. PV system, Genset, Wind Turbine system etc.> intended installation position and method according to <document, e.g. Installation Instruction, Microgrid design>
|  | MGC | Exclusion | Service | DER Installer - Pre-Sales | Providing offer, including but not limited to : DER installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | DER Installer - Pre-Sales | Evaluating and accepting DER installation offer (including commercial negotiation)
|  | MGC | Exclusion | Service | DER Installer - Execution | Gathering necessary information required for installing DER, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | DER Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | DER Installer - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | DER Installer - Execution | Approving submitted DER installation MoS
|  | MGC | Exclusion | Service | DER Installer - Execution | Performing DER installation tasks according to approved MoS
|  | MGC | Exclusion | Service | DER Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the DER installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | DER Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | DER Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | DER Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | DER Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | DER Installer - Handover | Accepting completion report
|  | MGC | Exclusion | Service | DER Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | DER Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | DER Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | DER Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | DER Installer - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | DER Installer - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | DER Cabler - Pre-Sales | Gathering necessary information required for connecting installed DER component or system, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | DER Cabler - Pre-Sales | Liaising with <DERs, e.g. PV system, Genset, Wind Turbine system etc.> installer to understand supplied <DERs, e.g. PV system, Genset, Wind Turbine system etc.> installation position and method according to <document, e.g. Installation Instruction, Microgrid design>
|  | MGC | Exclusion | Service | DER Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | DER Cabler - Pre-Sales | Evaluating and accepting DER cabling work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | DER Cabler - Execution | Gathering necessary information required for connecting DER, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | DER Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | DER Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | DER Cabler - Execution | Approving submitted DER cabling work MoS
|  | MGC | Exclusion | Service | DER Cabler - Execution | Performing DER cabling work tasks according to approved MoS
|  | MGC | Exclusion | Service | DER Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the DER connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | DER Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | DER Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | DER Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | DER Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | DER Cabler - Handover | Accepting completion report
|  | MGC | Exclusion | Service | DER Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | DER Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | DER Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | DER Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | DER Cabler - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | DER Cabler - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Exclusion | Service | DER Configurator - Pre-Sales | Gathering necessary information required for configuring connected DER component or system, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | DER Configurator - Pre-Sales | Liaising with <DERs, e.g. PV system, Genset, Wind Turbine system etc.> cabler to understand supplied <DERs, e.g. PV system, Genset, Wind Turbine system etc.> connection method according to <document, e.g. Installation Instruction, Microgrid design>
|  | MGC | Exclusion | Service | DER Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | DER Configurator - Pre-Sales | Evaluating and accepting DER configuration work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | DER Configurator - Execution | Gathering necessary information required for configure connected DER, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | DER Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | DER Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | DER Configurator - Execution | Approving submitted DER configuration work MoS
|  | MGC | Exclusion | Service | DER Configurator - Execution | Performing DER configuration work tasks according to approved MoS
|  | MGC | Exclusion | Service | DER Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | DER Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | DER Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | DER Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | DER Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | DER Configurator - Handover | Accepting completion report
|  | MGC | Exclusion | Service | DER Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | DER Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | DER Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | DER Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | DER Configurator - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | DER Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Exclusion | Hardware | ESS Supplier - Pre-Sales | Gathering necessary information required for designing and specifying ESS to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Hardware | ESS Supplier - Pre-Sales | Designing and specifying ESS as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | MGC | Exclusion | Hardware | ESS Supplier - Pre-Sales | Providing offer, including but not limited to : ESS to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability, maintenance contract for supplied hardware.
|  | MGC | Exclusion | Hardware | ESS Supplier - Pre-Sales | Evaluating and accepting ESS supplying offer (including commercial negotiation)
|  | MGC | Exclusion | Hardware | ESS Supplier - Execution | Gathering necessary information required for supplying ESS, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Hardware | ESS Supplier - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding ESS installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | MGC | Exclusion | Hardware | ESS Supplier - Execution | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Hardware | ESS Supplier - Execution | Approving submitted ESS supplying MoS
|  | MGC | Exclusion | Hardware | ESS Supplier - Execution | Performing ESS supplying tasks according to approved MoS
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Accepting completion report
|  | MGC | Exclusion | Hardware | ESS Supplier - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Hardware | ESS Supplier - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Hardware | ESS Supplier - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Hardware | ESS Supplier - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Hardware | ESS Supplier - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Hardware | ESS Supplier - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | ESS Installer - Pre-Sales | Gathering necessary information required for installing supplied ESS, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | ESS Installer - Pre-Sales | Liaising with ESS supplier to specify supplied ESS intended installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | ESS Installer - Pre-Sales | Providing offer, including but not limited to : ESS installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | ESS Installer - Pre-Sales | Evaluating and accepting ESS installation offer (including commercial negotiation)
|  | MGC | Exclusion | Service | ESS Installer - Execution | Gathering necessary information required for installing ESS, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | ESS Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | ESS Installer - Execution | Providing ESS installation MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | ESS Installer - Execution | Approving submitted ESS installation MoS
|  | MGC | Exclusion | Service | ESS Installer - Execution | Performing ESS installation tasks according to approved MoS
|  | MGC | Exclusion | Service | ESS Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the ESS installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | ESS Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | ESS Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | ESS Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | ESS Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | ESS Installer - Handover | Accepting completion report
|  | MGC | Exclusion | Service | ESS Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | ESS Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | ESS Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | ESS Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | ESS Installer - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | ESS Installer - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | ESS Cabler - Pre-Sales | Gathering necessary information required for connecting installed ESS, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | ESS Cabler - Pre-Sales | Liaising with ESS installer to understand supplied LITEON component(s) installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | ESS Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | ESS Cabler - Pre-Sales | Evaluating and accepting ESS cabling work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | ESS Cabler - Execution | Gathering necessary information required for connecting ESS, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | ESS Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | ESS Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | ESS Cabler - Execution | Approving submitted ESS cabling work MoS
|  | MGC | Exclusion | Service | ESS Cabler - Execution | Performing ESS cabling work tasks according to approved MoS
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the ESS connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Accepting completion report
|  | MGC | Exclusion | Service | ESS Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | ESS Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | ESS Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | ESS Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | ESS Cabler - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | ESS Cabler - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | ESS Configurator - Pre-Sales | Gathering necessary information required for configuring connected ESS, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | ESS Configurator - Pre-Sales | Liaising with ESS cabler to understand supplied ESS connection method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | ESS Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | ESS Configurator - Pre-Sales | Evaluating and accepting ESS configuration work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | ESS Configurator - Execution | Gathering necessary information required for configure connected ESS, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | ESS Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | ESS Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | ESS Configurator - Execution | Approving submitted ESS configuration work MoS
|  | MGC | Exclusion | Service | ESS Configurator - Execution | Performing ESS configuration work tasks according to approved MoS
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Accepting completion report
|  | MGC | Exclusion | Service | ESS Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | ESS Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | ESS Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | ESS Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | ESS Configurator - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | ESS Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Pre-Sales | Gathering necessary information required for designing and specifying Electrical DB to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Pre-Sales | Designing and specifying Electrical DB as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Pre-Sales | Providing offer, including but not limited to : Electrical DB to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability, maintenance contract for supplied hardware.
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Pre-Sales | Evaluating and accepting Electrical DB supplying offer (including commercial negotiation)
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Execution | Gathering necessary information required for supplying Electrical DB, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding Electrical DB installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Execution | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Execution | Approving submitted Electrical DB supplying MoS
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Execution | Performing Electrical DB supplying tasks according to approved MoS
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Accepting completion report
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Hardware | Electrical DB Supplier - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | Electrical DB Installer - Pre-Sales | Gathering necessary information required for installing supplied Electrical DB, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | Electrical DB Installer - Pre-Sales | Liaising with Electrical DB supplier to specify supplied Electrical DB intended installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | Electrical DB Installer - Pre-Sales | Providing offer, including but not limited to : Electrical DB installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | Electrical DB Installer - Pre-Sales | Evaluating and accepting Electrical DB installation offer (including commercial negotiation)
|  | MGC | Exclusion | Service | Electrical DB Installer - Execution | Gathering necessary information required for installing Electrical DB, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | Electrical DB Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | Electrical DB Installer - Execution | Providing Electrical DB installation MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | Electrical DB Installer - Execution | Approving submitted Electrical DB installation MoS
|  | MGC | Exclusion | Service | Electrical DB Installer - Execution | Performing Electrical DB installation tasks according to approved MoS
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the Electrical DB installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Accepting completion report
|  | MGC | Exclusion | Service | Electrical DB Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | Electrical DB Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | Electrical DB Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | Electrical DB Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | Electrical DB Installer - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | Electrical DB Installer - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | Electrical DB Cabler - Pre-Sales | Gathering necessary information required for connecting installed Electrical DB, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | Electrical DB Cabler - Pre-Sales | Liaising with Electrical DB installer to understand supplied LITEON component(s) installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | Electrical DB Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | Electrical DB Cabler - Pre-Sales | Evaluating and accepting Electrical DB cabling work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | Electrical DB Cabler - Execution | Gathering necessary information required for connecting Electrical DB, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | Electrical DB Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | Electrical DB Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | Electrical DB Cabler - Execution | Approving submitted Electrical DB cabling work MoS
|  | MGC | Exclusion | Service | Electrical DB Cabler - Execution | Performing Electrical DB cabling work tasks according to approved MoS
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the Electrical DB connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Accepting completion report
|  | MGC | Exclusion | Service | Electrical DB Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | Electrical DB Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | Electrical DB Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | Electrical DB Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | Electrical DB Cabler - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | Electrical DB Cabler - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | Electrical DB Configurator - Pre-Sales | Gathering necessary information required for configuring connected Electrical DB, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | Electrical DB Configurator - Pre-Sales | Liaising with Electrical DB cabler to understand supplied Electrical DB connection method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | Electrical DB Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | Electrical DB Configurator - Pre-Sales | Evaluating and accepting Electrical DB configuration work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | Electrical DB Configurator - Execution | Gathering necessary information required for configure connected Electrical DB, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | Electrical DB Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | Electrical DB Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | Electrical DB Configurator - Execution | Approving submitted Electrical DB configuration work MoS
|  | MGC | Exclusion | Service | Electrical DB Configurator - Execution | Performing Electrical DB configuration work tasks according to approved MoS
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Accepting completion report
|  | MGC | Exclusion | Service | Electrical DB Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | Electrical DB Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | Electrical DB Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | Electrical DB Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | Electrical DB Configurator - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | Electrical DB Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Inclusion | Hardware | LITEON Hardware | Supplying and delivering 1 (one) unit of Edge Gateway hardware Advantech ARK-1220F-S6A1 (or Axiomtek eBOX630-528-FL), come with power supply (230VAC, 50Hz input, Type G power plug) and DIN rail mounting bracket
|  | General | Inclusion | Hardware | LITEON Hardware | Supplying <other LITEON hardware, e.g. EV charger>
x | x
|  | General | Inclusion | Hardware | LITEON HW Supplier - Pre-Sales | Gathering necessary information required for designing and specifying LITEON component(s) to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Inclusion | Hardware | LITEON HW Supplier - Pre-Sales | Designing and specifying LITEON component(s) as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | General | Inclusion | Hardware | LITEON HW Supplier - Pre-Sales | Providing offer, including but not limited to : LITEON component(s) to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availbility, maintenance contract for supplied hardware.
|  | General | Inclusion | Hardware | LITEON HW Supplier - Pre-Sales | Evaluating and accepting LITEON component(s) supplying offer (including commercial negotiation)
|  | General | Inclusion | Hardware | LITEON HW Supplier - Execution | Gathering necessary information required for supplying LITEON component(s), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Inclusion | Hardware | LITEON HW Supplier - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding LITEON component(s) installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | General | Inclusion | Hardware | LITEON HW Supplier - Execution | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | General | Inclusion | Hardware | LITEON HW Supplier - Execution | Approving submitted LITEON component(s) supplying MoS
|  | General | Inclusion | Hardware | LITEON HW Supplier - Execution | Performing LITEON component(s) supplying tasks according to approved MoS
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Approving completion report template, as well as work evaluation criteria
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Accepting completion report
|  | General | Inclusion | Hardware | LITEON HW Supplier - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | General | Inclusion | Hardware | LITEON HW Supplier - After-Sales | Drafting maintenance tasks (scheduled)
|  | General | Inclusion | Hardware | LITEON HW Supplier - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | General | Inclusion | Hardware | LITEON HW Supplier - After-Sales | Signing maintenance contract, and or service level agreement
|  | General | Inclusion | Hardware | LITEON HW Supplier - After-Sales | Attending to ad-hoc service request
|  | General | Inclusion | Hardware | LITEON HW Supplier - After-Sales | Attending to scheduled maintenance tasks
|  | General | Exclusion | Service | LITEON HW Installer - Pre-Sales | Gathering necessary information required for installing supplied LITEON component(s), including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Exclusion | Service | LITEON HW Installer - Pre-Sales | Liaising with LITEON component(s) supplier to specify supplied LITEON component(s) intended installation position and method according to <document, e.g. Installation Instruction, design>
|  | General | Exclusion | Service | LITEON HW Installer - Pre-Sales | Providing offer, including but not limited to : LITEON component(s) installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | General | Exclusion | Service | LITEON HW Installer - Pre-Sales | Evaluating and accepting LITEON component(s) installation offer (including commercial negotiation)
|  | General | Exclusion | Service | LITEON HW Installer - Execution | Gathering necessary information required for installing LITEON component(s), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Exclusion | Service | LITEON HW Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | General | Exclusion | Service | LITEON HW Installer - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | General | Exclusion | Service | LITEON HW Installer - Execution | Approving submitted LITEON component(s) installation MoS
|  | General | Exclusion | Service | LITEON HW Installer - Execution | Performing LITEON component(s) installation tasks according to approved MoS
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the LITEON component(s) installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Accepting completion report
|  | General | Exclusion | Service | LITEON HW Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | General | Exclusion | Service | LITEON HW Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | General | Exclusion | Service | LITEON HW Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | General | Exclusion | Service | LITEON HW Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | General | Exclusion | Service | LITEON HW Installer - After-Sales | Attending to ad-hoc service request
|  | General | Exclusion | Service | LITEON HW Installer - After-Sales | Attending to scheduled maintenance tasks
|  | General | Exclusion | Service | LITEON HW Cabler - Pre-Sales | Gathering necessary information required for connecting installed LITEON component(s), including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Exclusion | Service | LITEON HW Cabler - Pre-Sales | Liaising with LITEON component(s) installer to understand supplied LITEON component(s) installation position and method according to <document, e.g. Installation Instruction, design>
|  | General | Exclusion | Service | LITEON HW Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | General | Exclusion | Service | LITEON HW Cabler - Pre-Sales | Evaluating and accepting LITEON component(s) cabling work offer (including commercial negotiation)
|  | General | Exclusion | Service | LITEON HW Cabler - Execution | Gathering necessary information required for connecting LITEON component(s), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Exclusion | Service | LITEON HW Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | General | Exclusion | Service | LITEON HW Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | General | Exclusion | Service | LITEON HW Cabler - Execution | Approving submitted LITEON component(s) cabling work MoS
|  | General | Exclusion | Service | LITEON HW Cabler - Execution | Performing LITEON component(s) cabling work tasks according to approved MoS
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the LITEON component(s) connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Accepting completion report
|  | General | Exclusion | Service | LITEON HW Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | General | Exclusion | Service | LITEON HW Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | General | Exclusion | Service | LITEON HW Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | General | Exclusion | Service | LITEON HW Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | General | Exclusion | Service | LITEON HW Cabler - After-Sales | Attending to ad-hoc service request
|  | General | Exclusion | Service | LITEON HW Cabler - After-Sales | Attending to scheduled maintenance tasks
|  | General | Exclusion | Service | LITEON HW Configurator - Pre-Sales | Gathering necessary information required for configuring connected LITEON component(s), including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Exclusion | Service | LITEON HW Configurator - Pre-Sales | Liaising with LITEON component(s) cabler to understand supplied LITEON component(s) connection method according to <document, e.g. Installation Instruction, design>
|  | General | Exclusion | Service | LITEON HW Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | General | Exclusion | Service | LITEON HW Configurator - Pre-Sales | Evaluating and accepting LITEON component(s) configuration work offer (including commercial negotiation)
|  | General | Exclusion | Service | LITEON HW Configurator - Execution | Gathering necessary information required for configure connected LITEON component(s), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Exclusion | Service | LITEON HW Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | General | Exclusion | Service | LITEON HW Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | General | Exclusion | Service | LITEON HW Configurator - Execution | Approving submitted LITEON component(s) configuration work MoS
|  | General | Exclusion | Service | LITEON HW Configurator - Execution | Performing LITEON component(s) configuration work tasks according to approved MoS
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Accepting completion report
|  | General | Exclusion | Service | LITEON HW Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | General | Exclusion | Service | LITEON HW Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | General | Exclusion | Service | LITEON HW Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | General | Exclusion | Service | LITEON HW Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | General | Exclusion | Service | LITEON HW Configurator - After-Sales | Attending to ad-hoc service request
|  | General | Exclusion | Service | LITEON HW Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Exclusion | Hardware | EGCP Supplier - Pre-Sales | Gathering necessary information required for designing and specifying Edge Gateway Control Panel (EGCP) to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Hardware | EGCP Supplier - Pre-Sales | Designing and specifying Edge Gateway Control Panel (EGCP) as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | MGC | Exclusion | Hardware | EGCP Supplier - Pre-Sales | Providing offer, including but not limited to : Edge Gateway Control Panel (EGCP) to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability, maintenance contract for supplied hardware.
|  | MGC | Exclusion | Hardware | EGCP Supplier - Pre-Sales | Evaluating and accepting Edge Gateway Control Panel (EGCP) supplying offer (including commercial negotiation)
|  | MGC | Exclusion | Hardware | EGCP Supplier - Execution | Gathering necessary information required for supplying Edge Gateway Control Panel (EGCP), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Hardware | EGCP Supplier - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding Edge Gateway Control Panel (EGCP) installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | MGC | Exclusion | Hardware | EGCP Supplier - Execution | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Hardware | EGCP Supplier - Execution | Approving submitted Edge Gateway Control Panel (EGCP) supplying MoS
|  | MGC | Exclusion | Hardware | EGCP Supplier - Execution | Performing Edge Gateway Control Panel (EGCP) supplying tasks according to approved MoS
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Accepting completion report
|  | MGC | Exclusion | Hardware | EGCP Supplier - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Hardware | EGCP Supplier - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Hardware | EGCP Supplier - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Hardware | EGCP Supplier - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Hardware | EGCP Supplier - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Hardware | EGCP Supplier - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | EGCP Installer - Pre-Sales | Gathering necessary information required for installing supplied Edge Gateway Control Panel (EGCP), including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | EGCP Installer - Pre-Sales | Liaising with Edge Gateway Control Panel (EGCP) supplier to specify supplied Edge Gateway Control Panel (EGCP) intended installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | EGCP Installer - Pre-Sales | Providing offer, including but not limited to : Edge Gateway Control Panel (EGCP) installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | EGCP Installer - Pre-Sales | Evaluating and accepting Edge Gateway Control Panel (EGCP) installation offer (including commercial negotiation)
|  | MGC | Exclusion | Service | EGCP Installer - Execution | Gathering necessary information required for installing Edge Gateway Control Panel (EGCP), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | EGCP Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | EGCP Installer - Execution | Providing Edge Gateway Control Panel (EGCP) installation MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | EGCP Installer - Execution | Approving submitted Edge Gateway Control Panel (EGCP) installation MoS
|  | MGC | Exclusion | Service | EGCP Installer - Execution | Performing Edge Gateway Control Panel (EGCP) installation tasks according to approved MoS
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the Edge Gateway Control Panel (EGCP) installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Accepting completion report
|  | MGC | Exclusion | Service | EGCP Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | EGCP Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | EGCP Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | EGCP Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | EGCP Installer - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | EGCP Installer - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | EGCP Cabler - Pre-Sales | Gathering necessary information required for connecting installed Edge Gateway Control Panel (EGCP), including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | EGCP Cabler - Pre-Sales | Liaising with Edge Gateway Control Panel (EGCP) installer to understand supplied LITEON component(s) installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | EGCP Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | EGCP Cabler - Pre-Sales | Evaluating and accepting Edge Gateway Control Panel (EGCP) cabling work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | EGCP Cabler - Execution | Gathering necessary information required for connecting Edge Gateway Control Panel (EGCP), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | EGCP Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | EGCP Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | EGCP Cabler - Execution | Approving submitted Edge Gateway Control Panel (EGCP) cabling work MoS
|  | MGC | Exclusion | Service | EGCP Cabler - Execution | Performing Edge Gateway Control Panel (EGCP) cabling work tasks according to approved MoS
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the Edge Gateway Control Panel (EGCP) connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Accepting completion report
|  | MGC | Exclusion | Service | EGCP Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | EGCP Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | EGCP Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | EGCP Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | EGCP Cabler - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | EGCP Cabler - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | EGCP Configurator - Pre-Sales | Gathering necessary information required for configuring connected Edge Gateway Control Panel (EGCP), including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | EGCP Configurator - Pre-Sales | Liaising with Edge Gateway Control Panel (EGCP) cabler to understand supplied Edge Gateway Control Panel (EGCP) connection method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | EGCP Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | EGCP Configurator - Pre-Sales | Evaluating and accepting Edge Gateway Control Panel (EGCP) configuration work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | EGCP Configurator - Execution | Gathering necessary information required for configure connected Edge Gateway Control Panel (EGCP), including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | EGCP Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | EGCP Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | EGCP Configurator - Execution | Approving submitted Edge Gateway Control Panel (EGCP) configuration work MoS
|  | MGC | Exclusion | Service | EGCP Configurator - Execution | Performing Edge Gateway Control Panel (EGCP) configuration work tasks according to approved MoS
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Accepting completion report
|  | MGC | Exclusion | Service | EGCP Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | EGCP Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | EGCP Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | EGCP Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | EGCP Configurator - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | EGCP Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Pre-Sales | Gathering necessary information required for designing and specifying EGCP Accessories to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name> | EGCP Accessories (e.g. UPS, network switch, HMI aka monitors)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Pre-Sales | Designing and specifying EGCP Accessories as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Pre-Sales | Providing offer, including but not limited to : EGCP Accessories to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability, maintenance contract for supplied hardware.
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Pre-Sales | Evaluating and accepting EGCP Accessories supplying offer (including commercial negotiation)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Execution | Gathering necessary information required for supplying EGCP Accessories, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding EGCP Accessories installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Execution | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Execution | Approving submitted EGCP Accessories supplying MoS
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Execution | Performing EGCP Accessories supplying tasks according to approved MoS
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Accepting completion report
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Hardware | EGCP Accessories Supplier - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Pre-Sales | Gathering necessary information required for installing supplied EGCP Accessories, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Pre-Sales | Liaising with EGCP Accessories supplier to specify supplied EGCP Accessories intended installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Pre-Sales | Providing offer, including but not limited to : EGCP Accessories installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Pre-Sales | Evaluating and accepting EGCP Accessories installation offer (including commercial negotiation)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Execution | Gathering necessary information required for installing EGCP Accessories, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Execution | Providing EGCP Accessories installation MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Execution | Approving submitted EGCP Accessories installation MoS
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Execution | Performing EGCP Accessories installation tasks according to approved MoS
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the EGCP Accessories installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Accepting completion report
|  | MGC | Exclusion | Service | EGCP Accessories Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | EGCP Accessories Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | EGCP Accessories Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | EGCP Accessories Installer - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | EGCP Accessories Installer - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Pre-Sales | Gathering necessary information required for connecting installed EGCP Accessories, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Pre-Sales | Liaising with EGCP Accessories installer to understand supplied LITEON component(s) installation position and method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Pre-Sales | Evaluating and accepting EGCP Accessories cabling work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Execution | Gathering necessary information required for connecting EGCP Accessories, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Execution | Approving submitted EGCP Accessories cabling work MoS
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Execution | Performing EGCP Accessories cabling work tasks according to approved MoS
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the EGCP Accessories connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Accepting completion report
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | EGCP Accessories Cabler - After-Sales | Attending to scheduled maintenance tasks
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Pre-Sales | Gathering necessary information required for configuring connected EGCP Accessories, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Pre-Sales | Liaising with EGCP Accessories cabler to understand supplied EGCP Accessories connection method according to <document, e.g. Installation Instruction, design>
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Pre-Sales | Evaluating and accepting EGCP Accessories configuration work offer (including commercial negotiation)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Execution | Gathering necessary information required for configure connected EGCP Accessories, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Execution | Approving submitted EGCP Accessories configuration work MoS
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Execution | Performing EGCP Accessories configuration work tasks according to approved MoS
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Accepting completion report
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - After-Sales | Attending to ad-hoc service request
|  | MGC | Exclusion | Service | EGCP Accessories Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Gathering necessary information required for performing MGC Integration and Commissioning service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Providing MGC Integration and Commissioning implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Providing offer, including but not limited to : providing documents such as Microgrid Controller System Architecture drawings and diagrams, Microgrid Controller operations and maintenance manual, Protection and control settings and coordination data, Cybersecurity plan and protocol, UAT report template, Project References; details and costs of service to be supplied in execution phase (e.g. Microgrid equipment and components functionality verification and rectification, communication testing between all connected components or devices, Microgrid Controller operation modes and scenarios validation, Microgrid fault and disturbances validation, Cybersecurity testing and implementation, arranging UAT activity and submitting UAT report according to approved template, Warranties and Life Cycle costs according to <document, e.g. design, proposal, tender>); project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning).
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Evaluating and accepting MGC Integration and Commissioning offer (including commercial negotiation)
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Gathering necessary information required for performing MGC Integration and Commissioning, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Performing MGC Integration and Commissioning, including but not limited to providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Providing MoS, states aligned execution method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Approving submitted MGC Integration and Commissioning MoS
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Performing MGC Integration and Commissioning tasks according to approved MoS
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Submitting completion report template <e.g. UAT report>, indicates the work evaluation criteria for approval <e.g. proofing and demonstrating commissioned MGC functionalities : Real-time monitoring and control, Load balancing, Remote Access, Power Quality Monitoring, Automatic reconfiguration (fault occurrence), Energy Storage Operational Optimization, Predictive maintenance, Scalability, Grid integration, and Cybersecurity>
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Arranging work evaluation activity (e.g. UAT)
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Attending work evaluation activity (e.g. UAT)
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Submitting completion report (including self or other party evaluation result, e.g. UAT with customer signature)
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Accepting completion report
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Attending to ad-hoc service request
|  | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Gathering necessary information required for designing and specifying Network Infrastructure to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Designing and specifying Network Infrastructure as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Providing offer, including but not limited to : Scope of work, Network design, Hardware and software components, Security and redundancy, Implementation plan, Cost breakdown, Service level agreements, Risks and assumptions, any materials or tools required in completing the supplied service, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability. Network Infrastructure hardware installation and cabling service to be supplied, DLP (Defect Liability Period) of the work been delivered, cable testing and test report, network devices configuration report, communication testing and test report, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract for the supplied hardware and services.
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Evaluating and accepting Network Infrastructure supplying offer (including commercial negotiation)
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Execution | Gathering necessary information required for supplying Network Infrastructure, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template. Providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work.
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Execution | Providing MoS, states aligned execution method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Execution | Approving submitted Network Infrastructure supplying MoS
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Execution | Performing Network Infrastructure supplying tasks according to approved MoS
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Execution | Submitting completion report template <e.g. cable testing and test report, network devices configuration report, communication testing and test report>, indicates the work evaluation criteria for approval <e.g. Cable tester indicates Pass, communication test success>
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Approving completion report template, as well as work evaluation criteria
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Arranging work evaluation activity (e.g. cable testing and communication testing)
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Attending work evaluation activity (e.g. cable testing and communication testing)
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Submitting completion report (including self or other party evaluation result, e.g. communication test report signature from connected device configurator)
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Accepting completion report
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Drafting maintenance tasks (scheduled)
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Drafting service level agreement (for ad-hoc service request)
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Signing maintenance contract, and or service level agreement
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Attending to ad-hoc service request
|  | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Attending to scheduled maintenance tasks
x | x
|  | General | Exclusion | Service | Internet Service Provider - Pre-Sales | Gathering necessary information required for providing Internet connection service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Exclusion | Service | Internet Service Provider - Pre-Sales | Providing Internet connection implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | General | Exclusion | Service | Internet Service Provider - Pre-Sales | Providing offer, including but not limited to : proposed speed and bandwidth, availability and coverage, cost and package options, contract and fees, reliability and uptime, customer support, security and privacy and additional features according to <document, e.g. design, proposal, tender>; project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning).
|  | General | Exclusion | Service | Internet Service Provider - Pre-Sales | Evaluating and accepting Internet connection offer (including commercial negotiation)
|  | General | Exclusion | Service | Internet Service Provider - Execution | Gathering necessary information required for providing Internet connection, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Exclusion | Service | Internet Service Provider - Execution | Providing Internet connection, including but not limited to providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work.
|  | General | Exclusion | Service | Internet Service Provider - Execution | Providing MoS, states aligned execution method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | General | Exclusion | Service | Internet Service Provider - Execution | Approving submitted Internet connection implementation MoS
|  | General | Exclusion | Service | Internet Service Provider - Execution | Performing Internet connection implementation tasks according to approved MoS
|  | General | Exclusion | Service | Internet Service Provider - Handover | Submitting completion report template <e.g. UAT report>, indicates the work evaluation criteria for approval <e.g. proofing and demonstrating provided Internet connection speed and bandwidth, uptime ratio>
|  | General | Exclusion | Service | Internet Service Provider - Handover | Approving completion report template, as well as work evaluation criteria
|  | General | Exclusion | Service | Internet Service Provider - Handover | Arranging work evaluation activity (e.g. UAT)
|  | General | Exclusion | Service | Internet Service Provider - Handover | Attending work evaluation activity (e.g. UAT)
|  | General | Exclusion | Service | Internet Service Provider - Handover | Submitting completion report (including self or other party evaluation result, e.g. UAT with customer signature)
|  | General | Exclusion | Service | Internet Service Provider - Handover | Accepting completion report
|  | General | Exclusion | Service | Internet Service Provider - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | General | Exclusion | Service | Internet Service Provider - After-Sales | Drafting maintenance tasks (scheduled)
|  | General | Exclusion | Service | Internet Service Provider - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | General | Exclusion | Service | Internet Service Provider - After-Sales | Signing maintenance contract, and or service level agreement
|  | General | Exclusion | Service | Internet Service Provider - After-Sales | Attending to ad-hoc service request
|  | General | Exclusion | Service | Internet Service Provider - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | General | Exclusion | Service | VAPT - Pre-Sales | Gathering necessary information required for performing VAPT service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | General | Exclusion | Service | VAPT - Pre-Sales | Providing VAPT implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | General | Exclusion | Service | VAPT - Pre-Sales | Providing offer, including but not limited to : Vendor Qualifications, Scope of Work, Technical Requirements (e.g. what is needed), Methodology (e.g. tools and techniques to be used), Deliverables (e.g. reports and summaries to be provided), Work Plan (milestones and timelines), Contract Terms; project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning).
|  | General | Exclusion | Service | VAPT - Pre-Sales | Evaluating and accepting VAPT offer (including commercial negotiation)
|  | General | Exclusion | Service | VAPT - Execution | Gathering necessary information required for performing VAPT, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | General | Exclusion | Service | VAPT - Execution | Performing VAPT, including but not limited to providing detailed project plan, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work.
|  | General | Exclusion | Service | VAPT - Execution | Providing MoS, states aligned execution method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | General | Exclusion | Service | VAPT - Execution | Approving submitted VAPT MoS
|  | General | Exclusion | Service | VAPT - Execution | Performing VAPT tasks according to approved MoS
|  | General | Exclusion | Service | VAPT - Handover | Submitting completion report template <e.g. scanning report> for approval
|  | General | Exclusion | Service | VAPT - Handover | Approving completion report template
|  | General | Exclusion | Service | VAPT - Handover | Submitting completion report
|  | General | Exclusion | Service | VAPT - Handover | Accepting completion report
|  |  | Exclusion |  | Electrical DB | Designing and specifying Electrical DB (Distribution Board) as well as installation position and method
|  |  | Exclusion |  | Electrical DB | Certifying or endorsing Electrical DB (Distribution Board) design specification as well as installation position and method
|  |  | Exclusion |  | Electrical DB | Supplying Electrical DB (Distribution Board) defined in <document, e.g. architecture diagram, electrical distribution diagram, or Microgrid design>
|  | MGC |  |  | Control Panel | Providing installation requirement (e.g. ventilation) for LITEON Edge Gateway hardware
[5 empty] | Control Panel | Designing and specifying <system name, e.g. MGC, CSMS, HEMS> control panel
[5 empty] | Control Panel | Certifying or Endorsing <system name, e.g. MGC, CSMS, HEMS> control panel design
[5 empty] | Control Panel | Supplying <LITEON device, e.g. Edge Gateway, or assembled control panel> according to <document, e.g. tendor, proposal, LOA>
[5 empty] | Control Panel | Souring for <system name, e.g. MGC, CSMS, HEMS> control panel maker
[5 empty] | Control Panel | Evaluating and accepting <system name, e.g. MGC, CSMS, HEMS> control panel maker offer
[5 empty] | Control Panel | Engaging control panel maker for <system name, e.g. MGC, CSMS, HEMS> control panel assembly
|  | General | Exclusion | Hardware | Control Panel | Supplying <system name> control panel installation accessories, including but not limited to enclosure, DIN rail, wall plugs, bolts and nuts, screws, cables, terminal blocks, RJ45 terminals, cable trunkings, cable conduits, tools needed to complete the installation work
[5 empty] | Control Panel | Souring for <system name, e.g. MGC, CSMS, HEMS> control panel installer
[5 empty] | Control Panel | Evaluating and accepting <system name, e.g. MGC, CSMS, HEMS> control panel installer offer
[5 empty] | Control Panel | Engaging control panel installer for <system name, e.g. MGC, CSMS, HEMS> control panel installation
[5 empty] | Control Panel | Submitting <LITEON device, e.g. Edge Gateway, or assembled control panel> installation MoS for approval
|  | General |  | Service | Control Panel | Installing <LITEON device, e.g. Edge Gateway, or assembled control panel> according to approved installation MoS
|  | MGC | Inclusion | Service | Control Panel | Guiding and assisting the <LITEON device, e.g. Edge Gateway, or assembled control panel> installation
[5 empty] | Control Panel | Submitting <LITEON device, e.g. Edge Gateway, or assembled control panel> installation report for acceptance
[5 empty] | Control Panel | Evaluating and accepting installation work (and report) as per defined in <LITEON device, e.g. Edge Gateway, or assembled control panel> installation MoS
[5 empty] | Accessories - Supply | Supplying <system name, e.g. MGC, CSMS, HEMS> accessories (e.g. UPS, network switch)
[5 empty] | Accessories - Supply | Souring for <system name, e.g. MGC, CSMS, HEMS> accessories vendor (e.g. UPS, network switch)
[5 empty] | Accessories - Supply | Evaluating and accepting <system name, e.g. MGC, CSMS, HEMS> accessories vendor offer
[5 empty] | Accessories - Installation | Souring for <system name, e.g. MGC, CSMS, HEMS> accessories installer
[5 empty] | Accessories - Installation | Evaluating and accepting <system name, e.g. MGC, CSMS, HEMS> accessories installer offer
[5 empty] | Accessories - Installation | Engaging accessories installer for <system name, e.g. MGC, CSMS, HEMS> accessories installation
[5 empty] | Accessories - Installation | Submitting <LITEON device, e.g. Edge Gateway, or assembled control panel> accessories installation MoS for approval
[5 empty] | Accessories - Installation | Approving <LITEON device, e.g. Edge Gateway, or assembled control panel> accessories installation MoS
[5 empty] | Accessories - Installation | Installing <LITEON device, e.g. Edge Gateway, or assembled control panel> accessories according to approved installation MoS
[5 empty] | Accessories - Installation | Guiding and assisting the <LITEON device, e.g. Edge Gateway, or assembled control panel> accessories installation
[5 empty] | Accessories - Installation | Submitting <LITEON device, e.g. Edge Gateway, or assembled control panel> accessories installation report for acceptance
[5 empty] | Accessories - Installation | Evaluating and accepting installation work (and report) as per defined in <LITEON device, e.g. Edge Gateway, or assembled control panel> installation MoS
|  |  |  | Software | LITEON System | Designing and specifying <system name, e.g. MGC, CSMS, HEMS>
|  |  |  | Software | LITEON System | Certifying or Endorsing <system name, e.g. MGC, CSMS, HEMS> design
|  |  |  | Software | LITEON System | Supplying <system name, e.g. MGC, CSMS, HEMS> according to definition in <document, e.g. compliance table, proposal>
|  |  | Exclusion | Software | LITEON System | Supplying any software, including but not limited to equipment configuration software, monitoring software, SCADA software, except the proposed <system name, e.g. MGC, CSMS, HEMS> and / or LITEON cloud platform
[5 empty] | LITEON System | Submitting <system name, e.g. MGC, CSMS, HEMS> software development MoS for approval
[5 empty] | LITEON System | Approving submitted <system name, e.g. MGC, CSMS, HEMS> software development MoS for approval
[5 empty] | LITEON System | Developing <software system name, e.g. MGC, CSMS, HEMS> according to approved development MoS
[5 empty] | LITEON System | Providing <system name, e.g. MGC, CSMS, HEMS> software design document
[5 empty] | LITEON System | Accepting provided <system name, e.g. MGC, CSMS, HEMS> software design document
[5 empty] | LITEON System | Providng <system name, e.g. MGC, CSMS, HEMS> software architecture diagram (different from system architecture diagram)
[5 empty] | LITEON System | Providing <software system name, e.g. MGC, CSMS, HEMS> source code
[5 empty] | LITEON System | Submitting <software system name, e.g. MGC, CSMS, HEMS> deployment MoS for approval
[5 empty] | LITEON System | Approving submitted <software system name, e.g. MGC, CSMS, HEMS> deployment MoS
[5 empty] | LITEON System | Deploying <software system name, e.g. MGC, CSMS, HEMS> according to approved deployment MoS
[5 empty] | After-Sales | Drafting Operation And Maintenance Agreement : SLA, Service Level Agreement
Attending commercial negotiation
Attending / arranging project kick-off meeting
|  | PM | Inclusion | Service | Project Management | Providing project management service
|  | PM | Inclusion | Service | Project Management | Conducting / attending <defining frequency, e.g. Weekly> project meeting
|  | PM |  |  | Project Management | Ensuring workforce complying with local safety requirement
|  | PM |  |  | Project Management | Applying safety permits and licenses
|  | PM |  |  | Project Management | Attending SIC, Site Introduction Course
|  | PM |  |  | Project Management | Conducting daily toolbox meeting
|  | PM |  |  | Project Management | Conducting risk assessment
|  | PM |  |  | Project Management | Managing risk via implementing the risk control measures
|  | PM |  |  | Project Management | Identifying roles and responsibilities (RACI)
|  | PM |  |  | Project Management | Identifying workflows
|  | PM |  |  | Project Management | Providing detailed project gantt-chart
[5 empty] | T and C | Providing data collection service for <system name>. Note : e.g. collecting data of charging station name, GPS coordinate, charger specification
[5 empty] | T and C | Providing data entry service for <system name>. Note : e.g. input collected data of charging station name, GPS coordinate, charger specification
|  |  |  | Hardware | Procurement | Purchasing and supplying <3rd party hardware, software>
|  |  |  | Service | Procurement | Providing technical specification of <LITEON or 3rd party hardware, software, e.g. server spec, Genset specification>
|  |  |  | Service | Procurement | Verifying or Endorsing <3rd party hardware, software> to be purchased by <entity name, e.g. customer, Installer>
|  |  |  | Service | Procurement | Arranging <any hardware, e.g. device, equipment, control panel> transportation
[5 empty] | Procurement | Arranging <any hardware, e.g. device, equipment, control panel> storage (before installation work been carried out)
[5 empty] | Execution | Applying and supplying <commercial-off-the-shelf software, normally one-time> certificate / license
[5 empty] | Execution | Subscribing and supplying <3rd party service name, normally subscription, e.g. AWS, eWallet> ceritifcate / license
[5 empty] | Outsourcing | Preparing Request For Proposal (RFP) for <service, e.g. installation, cabling etc. normally one-time>
[5 empty] | Outsourcing | Requesting Proposal for <service, e.g. installation, cabling etc. normally one-time>
[5 empty] | Outsourcing | Accepting proposal and engaging <3rd party company name> for <service, e.g. installation, cabling etc. normally one-time>
|  |  |  | Service | After-Sales | Preparing Request For Proposal (RFP) for <service, e.g. call center, maintenance etc. normally subscription>
|  |  |  | Service | After-Sales | Requesting Proposal for <after-sales service, e.g. call center, maintenance etc. normally subscription>
|  |  |  | Service | After-Sales | Evaluating and accepting <after-sales service provider name> offer
|  |  |  | Service | After-Sales | Engaging <after-sales service provider name> for <after-sales service, e.g. call center, maintenance etc. normally subscription>
|  |  |  | Hardware | Installation | Supplying <3rd party devices, equipment> according to <document, e.g. tendor, proposal, LOA>
|  |  |  | Process | Installation | Submitting <3rd party devices, equipment> installation MoS (including installation position and method) for approval
|  |  |  | Process | Installation | Approving submitted <3rd party devices, equipment> installation MoS (including installation position and method)
|  |  |  | Service | Installation | Installing <3rd party devices, equipment> according to approved installation MoS
|  |  |  | Process | Installation | Evaluating and accepting installation work as per defined in <3rd party devices, equipment> installation MoS
[5 empty] | Cabling | Designing and specifying <type of cable, e.g. AC, DC, field communication network> according to <document, e.g. Microgrid design, proposal>. Note : Field communication network distance limitation should be considered.
[5 empty] | Cabling | Certifying or Endorsing <type of cable, e.g. AC, DC, field communication network> cable specification
[5 empty] | Cabling | Supplying cables for <type of cable, e.g. AC, DC, field communication network> according to <document, e.g. Microgrid design, proposal>
[5 empty] | Cabling | Submitting <type of cabling work, e.g. AC, DC and communication network> cabling work MoS for approval
[5 empty] | Cabling | Approving submitted <type of cabling work, e.g. AC, DC and communication network> cabling work MoS
[5 empty] | Cabling | Connecting <field devices, equipment name, both LITEON or 3rd party> to eletrical distribution network according to approved cabling work MoS
[5 empty] | Cabling | Connecting <field devices, equipment name, both LITEON or 3rd party> to <field communication network name, e.g. Modbus TCP, Modbus RTU over RS485> according to approved cabling work MoS
[5 empty] | Cabling | Guiding and assisting the <field devices, equipment name, both LITEON or 3rd party> <field communication network name, e.g. Modbus TCP, Modbus RTU over RS485> connection and termination work
|  |  | Assumption / Customer Responsibility |  | Cabling | Join T&C activity between LITEON and network supplier is expected to ensure all connected devices are able to communicate via established network.
[5 empty] | Cabling | Evaluating and accepting cabling work as per defined in <type of cabling work, e.g. AC, DC and communication network> cabling work MoS
[5 empty] | Internet | Providing Internet connection design for <system name> according to <document, e.g. proposal, network infrastructure diagram>. Note : Minimum Internet speed is (?)100 Mbps.
[5 empty] | Internet | Submitting <project name> network infrastructure work MoS for approval
[5 empty] | Internet | Setting up Internet network infrastructure for <project name> according to approved network infrastructure work MoS
[5 empty] | Internet | Evaluating and accepting network infrastructure work as per defined in <project name> network infrastructure work MoS
|  |  | Exclusion | Service | T and C - 3rd party device, equipment | Submitting <3rd party devices, equipment> testing and commissioning MoS (including field network communication configuration) for approval
|  |  | Exclusion | Service | T and C - 3rd party device, equipment | Performing testing and commissioning work for <3rd party devices, equipment, to serve its function> according to approved testing and commissioning MoS
|  |  | Exclusion | Service | T and C - 3rd party device, equipment | Evaluating and accepting testing and commissioning work as per defined in <3rd party devices, equipment> testing and commissioning work MoS
|  |  | Exclusion | Service | T and C | Configuring network devices which been supplied by other party, even the purpose is to fit LITEON’s needs
|  | MGC | Assumption / Customer Responsibility | Service | Integration | <3rd party device or equipment, e.g. Genset Controllers, PV and BESS Inverters, smart DBs and other DERs devices> <protocol name, e.g. Modbus, IEC104> <document, e.g Modbus Register table, IEC104 Information Objects and Data Elements table> should be made available for LITEON
[5 empty] | Integration | Submitting <3rd party devices, equipment> integration MoS (mainly pertaining to LITEON systems, e.g. MGC, CSMS, HEMS) for approval
[5 empty] | Integration | Performing integration work for <3rd party devices, equipment, to serve its function> according to approved integration MoS
|  | General | Assumption / Customer Responsibility | Service | Integration | Join Integration test between <LITEON> and <3rd party device or equipment supplier, e.g. Genset Controllers, PV and BESS Inverters, smart DBs and other DERs suppliers> is expected to ensure system integrity
[5 empty] | Integration | Evaluating and accepting integration work as per defined in <3rd party devices, equipment> testing and commissioning work MoS
|  |  | Exclusion | Service | Integration | Acquiring data from, and / or sending data to, any device with new communication protocol which not been defined in <document, e.g. tendor, proposal, integration MoS>. Note : normally this adaptation involves development effort, testing, trial, pilot etc. and cannot guarantee the result
|  |  | Exclusion | Service | Integration | Acquiring data from, and / or sending data to, newly added devices which not been defined in <document, e.g. tendor, proposal, integration MoS> via defined communication protocol
|  |  | Exclusion | Service | Integration | Acquiring data from, and / or sending data to, new data points not been defined in <document, e.g. tendor, proposal, integration MoS> within connected network devices
|  |  | Assumption / Customer Responsibility |  | Integration | LITEON only acquires the data from connected components but not sending any command so not responsible for any damage of the connected components;
|  |  | Inclusion | Service | Integration | LITEON will maintain confidentiality of the acquired data and will not disclose it to third parties, except as stated in this proposal or any other written agreement between LITEON and <customer name>, unless legally obligated to do so
|  |  | Assumption / Customer Responsibility |  | Integration | Providing accurate and sufficient information to LITEON team upon request, including but not limited to connected devices datasheet, Modbus register table, IP address and Slave IDs of connected devices, SLD of the existing setup, load profile and future expansion plan
[5 empty] | T and C | Submitting <system name> testing and commissioning MoS (including field network communication configuration) for approval
[5 empty] | T and C | Performing testing and commissioning work for <system name> according to approved testing and commissioning MoS
[5 empty] | T and C | Evaluating and accepting testing and commissioning work as per defined in <system name> testing and commissioning work MoS
|  |  | Assumption / Customer Responsibility |  | T and C | <customer name> shall permit LITEON, and any persons authorised by it, at all reasonable times to have access to the acquired data and database either at the <customer name> location or Cloud for analysis and other necessary purpose
|  |  | Assumption / Customer Responsibility |  | T and C | Testing the <system name, e.g. PV SCADA> <feature 1, e.g. UI>, <feature2 and more> and providing timely feedbacks upon LITEON’s request within <3> working days
|  |  | Assumption / Customer Responsibility |  | T and C | Providing on-demand onsite assistance for simple tasks such as simulating events, faults etc.
[5 empty] | VAPT | Preparing Request For Proposal (RFP) for VAPT
[5 empty] | VAPT | Souring for VAPT vendor
[5 empty] | VAPT | Submitting VAPT criteria to <customer name> for approval
[5 empty] | VAPT | Approving submitted VAPT criteria
[5 empty] | VAPT | Evaluating and accepting <VAPT vendor name> offer
[5 empty] | VAPT | Engaging <VAPT vendor name> for <system name, e.g. MGC, CSMS, HEMS> VAPT
[5 empty] | Payment | Submitting progress payment invoice (together with the milestone completion evidence) according to definition in <document, e.g. tender, proposal, quotation>
[5 empty] | Payment | Making progress payment
[5 empty] | Payment | Receiving progress payment and producing receipt
[5 empty] | Execution | Modifying or Adding deliverables beyond the definition in <document, e.g. tender, proposal>
[5 empty] | Handover | Providing UAT template according to <document, e.g. tender, proposal, compliance table> for approval
[5 empty] | Handover | Approving submitted UAT template
[5 empty] | Handover | Attending / arranging UAT activity
[5 empty] | Handover | Completing and submitting UAT report
[5 empty] | Handover | Accepting UAT report
[5 empty] | Handover | Preparing user training material (e.g. Operation manual, troubleshooting manual) for <organization, e.g. end user operation team, end user IT team>
[5 empty] | Handover | Arranging user training
[5 empty] | Handover | Attending user training
[5 empty] | Handover | Conducting user training
[5 empty] | Handover | Preparing As-built materials (e.g. drawings, design documents, manuals)
[5 empty] | Handover | Submitting As-built materials
[5 empty] | Handover | Accepting submitted As-built materials
[5 empty] | Handover | Preparing internal handover to LITEON operation team
[5 empty] | Handover | Handing over to LITEON operation team
Requesting ad-hoc service or support
Attending to ad-hoc service or support request
Assisting ad-hoc service or support request
Submitting ad-hoc service or support report
Submitting Certificate of Final Completion
Accepting Certificate of Final Completion
[5 empty] | After-Sales VAPT | Drafting vulnerability patching service agreement
[5 empty] | After-Sales VAPT | Proposing vulnerability patching service agreement
[5 empty] | After-Sales VAPT | Attending vulnerability patching service
[5 empty] | After-Sales VAPT | Submitting vulnerability patching service report
[5 empty] | After-Sales VAPT | Accepting vulnerability patching service report
Defining <service level definition, e.g. 24/7, or refer to SLMA> maintenance support
Providing <service level definition, e.g. 24/7, or refer to SLMA> maintenance support
Drafting maintenance contract
Proposing maintenance contract
Attending scheduled maintenance activity
Submitting scheduled maintenance report
Accepting scheduled maintenance report
Proposing license / maintenance contract renewal
Accepting license / maintenance contract renewal
Requesting to modify or add features / deliverables beyond the delivered <system name>. Note : to be considered as a new project and go through the full cycle.
Contingency
Contingency
Contingency
Contingency
Contingency
Contingency
Contingency

## SOP
If suppling something (hardware, software, service)
Hardware : only selling the hardware. For installing, connecting, configuring the supplied hardware are considered as associated "Service"
Software : only selling the software. For developing, deploying and configuring the supplied software are considered as associated "Service"
Service : anything other than an off-the-shelf product (hardware or software), normally involves site work, therefore project management and safety aspect needs to be considered
Note : single supplier can provide more than one category of the product. Example : a desktop supplier provides desktop (hardware), embedded OS (software) and installation at dedicated location (service)
Pre-sales
Gathering or feeding information
Performing high level design
Providing offer which covers :
Hardware : hardware, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availbility, maintenance contract for supplied hardware.
Software : software, license, subscription, deployment, training or support, debugging, security patching
Service : service, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management, drawings, MoS, completion report, maintenance contract
Evaluating and accepting offer (including commercial negotiation)
Execution
Gathering or feeding details
Performing low level design
Certifying or endorsing low level design
Submitting MoS (includes :
Equipment logistic
Software license, subscription, if applicable
Labour work permit, license, certificate etc.
Safety certificate, Permit-To-Work
Work steps
Risks for each step
Control measure for each risk
Contingency plan
Evaluation criteria)
Approving MoS
Carrying out work steps according to approved MoS
Progress meeting
Handover
Submitting completion report template, indicates the work evaluation criteria for approval
Approving completion report template, as well as work evaluation criteria
Arranging work evaluation activity (e.g. UAT)
Attending work evaluation activity (e.g. UAT)
Submitting completion report (including self or other party evaluation result, e.g. UAT)
Accepting completion report
Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
After-Sales
Drafting maintenance tasks (scheduled)
Requires R&D to provide per task man-hour
Drafting service level agreement (for ad-hoc service request)
Signing maintenance contract, and or service level agreement
Attending to ad-hoc service request
Attending to scheduled maintenance tasks

## Scope List
Latest update : 24-Jul-2023, Gabriel
| System | Items | Note
| MGC | All listed equipment, devices, components and 3rd party systems (Genset, BESS, PV, DB, UPS, Network Switch, PLC, SCADA etc.) are to be supplied, installed and commissioned by 3rd party, except suppling and commissioning Edge Advance (Microgrid Controller) to be done by LITEON
| MGC | The Genset Controllers, PV and BESS Inverters, smart DBs and other DERs should be Modbus TCP / Modbus RS485 / IEC 104 / IEC 101 compatible. Communication parameter configuration to be discussed with and defined by LITEON. Any incompatible component should be excluded from Microgrid Controller control network.
v | MGC | DER hardware (e.g. PV system and inverter, Genset and Genset controller), installation, cabling work (AC, DC and communication), integration
v | MGC | ESS hardware (e.g. BESS system and inverter), installation, cabling work (AC, DC and communication), integration
v | MGC | Electrical Distribution Board (Smart), installation, cabling work (AC, DC and communication), integration
v | MGC | Supplying Edge Gateway itself
v | MGC | Edge Gateway Control Panel (EGCP) assembly, installation, cabling work (AC, DC and communication), integration
v | MGC | EGCP Accessories (e.g. UPS, network switch, HMI such as laptops or monitors), installation, cabling work (AC, DC and communication), integration UPS : if mains cut-off, need to inform Edge Gateway, can consider dry contact
v | MGC | Microgrid Controller Integration and final UAT
v | General | Network Infrastructure (LAN) service
v | General | Internet service
v | General | VAPT
Energy audit
Power supply (230 VAC, 50 Hz)
Data collection service (e.g. collecting the load profile, checking available room for installation, surveying and confirming the EV charging station installation method etc.)
Data correction service (i.e. confirming whether the provided data is correct via in-house data analysis, and or onsite verification)
Data entry service (i.e. performing manual configuration work required on behave of customer, such as creating devices, adding charging station)
Data import / export service (e.g. importing or exporting data other than standard system features. Note : high possibility that development work involved, can consider it as a small project)
Data conversion service (e.g. converting standard API response data format to meet the request. Note : normally development work involved, can consider it as a small project)
Ad-hoc troubleshooting service
(Pre-Concept Design) Artistic impression, power point or video/3D rendering
(Pre-Concept Design) Supporting presentations/meetings at customer’s site
(Pre-Detail Design) BOQ, Layout & Wiring Diagram, Integration plan
(Pre-Documentation) Special technical documents for pitching or proposal submittal
(Pre-Site Visit) Audit support, Feasibility assessments
(Pre-Travel) Travel time and accommodation required for presales activities
(Exe-Training) Control Panel assembly & Installation training

## SOP interpreter
| Latest update : 20-Jul-2023, Gabriel | [5 empty] | has formula
|  | Supplied Item | System | Scope | Category | Phase | Task | Note
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Gathering necessary information required for designing and specifying Network Infrastructure to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Designing and specifying Network Infrastructure as well as drafting installation position and method according to <document, e.g. design, proposal, tender>
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Providing offer, including but not limited to : Network Infrastructure to be supplied, supplied hardware warranty, supplied hardware datasheet, supplied hardware certificates, supplied hardware communication document, supplied hardware user manual, logistic arrangement for supplied hardware, supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability, maintenance contract for supplied hardware. | supplied hardware operation training, supplied hardware troubleshooting and emergency response training, supplied hardware spare part management, supplied hardware End-Of-Life or Phase-In/Phase-Out roadmap and substitution hardware availability, maintenance contract for supplied hardware.
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Evaluating and accepting Network Infrastructure supplying offer (including commercial negotiation)
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Gathering necessary information required for supplying Network Infrastructure, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, feeding Network Infrastructure installer and other parties with necessary document, such as Commercial invoice, Delivery Order, Certificate of origin, Packing list, Import license, FAT Test Report, Installation Instructions, Configuration Manual, SAT Report Template
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Providing MoS, states aligned delivery schedule, logistic and warehousing arrangement as well as the risks, control measures implementation method and contingency plan
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Approving submitted Network Infrastructure supplying MoS
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Performing Network Infrastructure supplying tasks according to approved MoS
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Submitting completion report template <e.g. DO with warehouse photos>, indicates the work evaluation criteria for approval <e.g. delivered goods are in good condition, goods storage been arranged properly>
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Approving completion report template, as well as work evaluation criteria
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Arranging work evaluation activity (e.g. goods quantity and condition inspection)
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Attending work evaluation activity (e.g. goods quantity and condition inspection)
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Submitting completion report (including self or other party evaluation result, e.g. DO with recipient signature)
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Accepting completion report
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Drafting maintenance tasks (scheduled)
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Drafting service level agreement (for ad-hoc service request)
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Signing maintenance contract, and or service level agreement
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Attending to ad-hoc service request
|  | Network Infrastructure | General | Exclusion | Hardware | Network Infrastructure Provider - Pre-Sales | Attending to scheduled maintenance tasks
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Pre-Sales | Gathering necessary information required for installing supplied Network Infrastructure, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Pre-Sales | Liaising with Network Infrastructure supplier to specify supplied Network Infrastructure intended installation position and method according to <document, e.g. Installation Instruction, design>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Pre-Sales | Providing offer, including but not limited to : Network Infrastructure installation service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract | project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Pre-Sales | Evaluating and accepting Network Infrastructure installation offer (including commercial negotiation)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Execution | Gathering necessary information required for installing Network Infrastructure, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Execution | Providing detailed project plan, including but not limited to identifying hardware delivery timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Execution | Providing Network Infrastructure installation MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Execution | Approving submitted Network Infrastructure installation MoS
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Execution | Performing Network Infrastructure installation tasks according to approved MoS
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Submitting completion report template (e.g. pre-installation location photos and installed hardware photos), indicates the work evaluation criteria for approval (e.g. meeting the Network Infrastructure installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration) | installation requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Approving completion report template, as well as work evaluation criteria
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Arranging work evaluation activity (e.g. site inspection)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Attending work evaluation activity (e.g. site inspection)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Accepting completion report
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - After-Sales | Drafting maintenance tasks (scheduled)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - After-Sales | Signing maintenance contract, and or service level agreement
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - After-Sales | Attending to ad-hoc service request
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Installer - After-Sales | Attending to scheduled maintenance tasks
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Pre-Sales | Gathering necessary information required for connecting installed Network Infrastructure, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Pre-Sales | Liaising with Network Infrastructure installer to understand supplied LITEON component(s) installation position and method according to <document, e.g. Installation Instruction, design>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Pre-Sales | Evaluating and accepting Network Infrastructure cabling work offer (including commercial negotiation)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Execution | Gathering necessary information required for connecting Network Infrastructure, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | , including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Execution | Providing detailed project plan, including but not limited to identifying hardware installation timeline, liaising with site manager regarding logistic, warehousing and performing work task arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Execution | Approving submitted Network Infrastructure cabling work MoS
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Execution | Performing Network Infrastructure cabling work tasks according to approved MoS
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Submitting completion report template (e.g. cable routing diagram, cable piping or trunking photos, labeling and termination photos), indicates the work evaluation criteria for approval (e.g. meeting the Network Infrastructure connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration) | connection requirement in Installation Instruction, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Approving completion report template, as well as work evaluation criteria
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Accepting completion report
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - After-Sales | Drafting maintenance tasks (scheduled)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - After-Sales | Signing maintenance contract, and or service level agreement
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - After-Sales | Attending to ad-hoc service request
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Cabler - After-Sales | Attending to scheduled maintenance tasks
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Pre-Sales | Gathering necessary information required for configuring connected Network Infrastructure, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name> | , including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Pre-Sales | Liaising with Network Infrastructure cabler to understand supplied Network Infrastructure connection method according to <document, e.g. Installation Instruction, design>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Pre-Sales | Providing offer, including but not limited to : service to be supplied, DLP (Defect Liability Period), any materials or tools required in completing the supplied service, project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning), drawings, MoS, completion report, maintenance contract
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Pre-Sales | Evaluating and accepting Network Infrastructure configuration work offer (including commercial negotiation)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Execution | Gathering necessary information required for configure connected Network Infrastructure, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | , including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Execution | Providing detailed project plan, including but not limited to identifying hardware connection timeline, liaising with site manager regarding service activity arrangement, acquiring necessary document and approvals, such as Permit-To-Work.
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Execution | Providing MoS, states aligned work schedule, any other arrangement as well as the risks, control measures implementation method and contingency plan
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Execution | Approving submitted Network Infrastructure configuration work MoS
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Execution | Performing Network Infrastructure configuration work tasks according to approved MoS
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Submitting completion report template (e.g. UAT template that includs design interpretation, parameters to be configured and its value), indicates the work evaluation criteria for approval (e.g. meeting the design requirement, work been completed on schedule and within budget, completed work complies with local standards, work been carried out in a safe manner, work been done with minimum interruption to other party's work and even the aesthetic consideration)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Approving completion report template, as well as work evaluation criteria
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Arranging work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Attending work evaluation activity (e.g. onsite inspection, energizing test, communication test, UAT)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Submitting completion report (including self or other party evaluation result, e.g. site inspection comments and rectification work been done)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Accepting completion report
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - After-Sales | Drafting maintenance tasks (scheduled)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - After-Sales | Signing maintenance contract, and or service level agreement
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - After-Sales | Attending to ad-hoc service request
|  | Network Infrastructure | General | Exclusion | Service | Network Infrastructure Configurator - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Pre-Sales | Gathering necessary information required for designing and specifying 3rd party software to be supplied, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Pre-Sales | Designing and specifying 3rd party software as well as development and deployment method and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Pre-Sales | Providing offer, including but not limited to : 3rd party software to be supplied together with the compliance table and / or the feature list, supplied software warranty or DLP (Defect Liability Period), supplied software licensing terms and conditions, supplied software subscription terms and conditions, supplied software certificates, supplied software SDK or API document, supplied software user manual, development and / or deployment arrangement for supplied software, supplied software operation and troubleshooting training, supplied software dependency management, supplied software End-Of-Life or Phase-In/Phase-Out roadmap and substitution software availability, maintenance contract for supplied software. | , supplied software subscription terms and conditions, supplied software certificates, supplied software SDK or API document, supplied software user manual, development and / or deployment arrangement for supplied software, supplied software operation and troubleshooting training, supplied software dependency management, supplied software End-Of-Life or Phase-In/Phase-Out roadmap and substitution software availability, maintenance contract for supplied software.
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Pre-Sales | Evaluating and accepting 3rd party software supplying offer (including commercial negotiation)
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Execution | Gathering necessary information required for supplying 3rd party software, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Execution | Providing detailed project plan, including but not limited to identifying software delivery timeline, liaising with customer project manager regarding development, deployment and other work task arrangement, providing other parties with necessary document, such as Commercial invoice, Delivery Order, Compliance certificates, Software License Agreement, Deployment Instructions, Release Notes or Change Logs, Configuration Manual, SDK/API document, SAT Report Template, SLA (Service Level Agreement), Support & Maintenance Agreement
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Execution | Providing MoS, states aligned deployment method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Execution | Approving submitted 3rd party software supplying MoS
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Execution | Performing 3rd party software supplying tasks according to approved MoS
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Submitting completion report template <e.g. UAT report>, indicates the work evaluation criteria for approval <e.g. delivered software complies with requested features and proofs of each compliance>
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Approving completion report template, as well as work evaluation criteria
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Arranging work evaluation activity (e.g. UAT)
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Attending work evaluation activity (e.g. UAT)
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Submitting completion report (including self or other party evaluation result, e.g. UAT with customer signature)
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Accepting completion report
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - After-Sales | Drafting maintenance tasks (scheduled)
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - After-Sales | Signing maintenance contract, and or service level agreement
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - After-Sales | Attending to ad-hoc service request
|  | 3rd party software | General | Inclusion | Software | Software supplier and deployer - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Pre-Sales | Gathering necessary information required for designing and specifying high level Microgrid Design and consultation service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Pre-Sales | Providing high level Microgrid Design and consultation service as well as implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Pre-Sales | Providing offer, including but not limited to : Microgrid Design and consultation service Feasibility Study Report, Microgrid System Architecture, Microgrid System Components, Conceptual Design Report, Project References, (Optional) Financial Models, details and cost of Microgrid Design and consultation service to be supplied in execution phase (e.g. System Design Documents, Microgrid System Component Technical Specifications, Control System Documentation, Integration Documentation, Commissioning and Acceptance Test Plans, Operations and Maintenance Documentation, Cybersecurity Documentation, Warranties and Life Cycle costs), project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning). More details refer to Sheet "MicrogridDesignDocs" | Feasibility Study Report, Microgrid System Architecture, Microgrid System Components, Conceptual Design Report, Project References, (Optional) Financial Models, details and cost of Microgrid Design and consultation service to be supplied in execution phase (e.g. System Design Documents, Microgrid System Component Technical Specifications, Control System Documentation, Integration Documentation, Commissioning and Acceptance Test Plans, Operations and Maintenance Documentation, Cybersecurity Documentation, Warranties and Life Cycle costs), project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning). More details refer to Sheet "MicrogridDesignDocs"
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Pre-Sales | Evaluating and accepting Microgrid Design and consultation service offer (including commercial negotiation)
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Execution | Gathering necessary information required for performing Microgrid Design and consultation service, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | , including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Execution | Performing Microgrid Design and consultation service, providing System Design Documents, Microgrid System Component Technical Specifications (e.g. brand and model of DERs; Smart Electrical Distribution Board; Cables; other accessories and intended high level installation position and method), Control System Documentation, Integration Documentation, Commissioning and Acceptance Test Plans, Operations and Maintenance Documentation, Cybersecurity Documentation, Warranties and Life Cycle costs according to <document, e.g. design, proposal, tender> | , providing System Design Documents, Microgrid System Component Technical Specifications (e.g. brand and model of DERs; Smart Electrical Distribution Board; Cables; other accessories and intended high level installation position and method), Control System Documentation, Integration Documentation, Commissioning and Acceptance Test Plans, Operations and Maintenance Documentation, Cybersecurity Documentation, Warranties and Life Cycle costs according to <document, e.g. design, proposal, tender>
|  | Microgrid Design and consultation service | General | Exclusion | Service | Microgrid Design - Execution | Liaising with <certifying party, normally consultant from customer> to certify or endorse submitted Microgrid design
x | x
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Gathering necessary information required for performing MGC Integration and Commissioning service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Providing MGC Integration and Commissioning implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Providing offer, including but not limited to : providing documents such as Microgrid Controller System Architecture drawings and diagrams, Microgrid Controller operations and maintenance manual, Protection and control settings and coordination data, Cybersecurity plan and protocol, UAT report template, Project References; details and costs of service to be supplied in execution phase (e.g. Microgrid equipment and components functionality verification and rectification, communication testing between all connected components or devices, Microgrid Controller operation modes and scenarios validation, Microgrid fault and disturbances validation, Cybersecurity testing and implementation, arranging UAT activity and submitting UAT report according to approved template, Warranties and Life Cycle costs according to <document, e.g. design, proposal, tender>); project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning). | providing documents such as Microgrid Controller System Architecture drawings and diagrams, Microgrid Controller operations and maintenance manual, Protection and control settings and coordination data, Cybersecurity plan and protocol, UAT report template, Project References; details and costs of service to be supplied in execution phase (e.g. Microgrid equipment and components functionality verification and rectification, communication testing between all connected components or devices, Microgrid Controller operation modes and scenarios validation, Microgrid fault and disturbances validation, Cybersecurity testing and implementation, arranging UAT activity and submitting UAT report according to approved template, Warranties and Life Cycle costs according to <document, e.g. design, proposal, tender>); project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning).
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Pre-Sales | Evaluating and accepting MGC Integration and Commissioning offer (including commercial negotiation)
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Gathering necessary information required for performing MGC Integration and Commissioning, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | , including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Performing MGC Integration and Commissioning, including but not limited to providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work. | , including but not limited to providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work.
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Providing MoS, states aligned execution method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Approving submitted MGC Integration and Commissioning MoS
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Execution | Performing MGC Integration and Commissioning tasks according to approved MoS
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Submitting completion report template <e.g. UAT report>, indicates the work evaluation criteria for approval <e.g. proofing and demonstrating commissioned MGC functionalities : Real-time monitoring and control, Load balancing, Remote Access, Power Quality Monitoring, Automatic reconfiguration (fault occurrence), Energy Storage Operational Optimization, Predictive maintenance, Scalability, Grid integration, and Cybersecurity>
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Approving completion report template, as well as work evaluation criteria
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Arranging work evaluation activity (e.g. UAT)
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Attending work evaluation activity (e.g. UAT)
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Submitting completion report (including self or other party evaluation result, e.g. UAT with customer signature)
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Accepting completion report
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Drafting maintenance tasks (scheduled)
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Signing maintenance contract, and or service level agreement
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Attending to ad-hoc service request
|  | MGC Integration and Commissioning | MGC | Inclusion | Service | MGC Integration and Commissioning - After-Sales | Attending to scheduled maintenance tasks
x | x
|  | VAPT | General | Exclusion | Service | VAPT - Pre-Sales | Gathering necessary information required for performing VAPT service, including but not limited to attending project briefing, receiving project documents, attending site survey, setting up demo/trial/pilot, as per requested by <customer name>
|  | VAPT | General | Exclusion | Service | VAPT - Pre-Sales | Providing VAPT implementation plan and schedule according to <document, e.g. design, proposal, tender>, if applicable
|  | VAPT | General | Exclusion | Service | VAPT - Pre-Sales | Providing offer, including but not limited to : proposed speed and bandwidth, availability and coverage, cost and package options, contract and fees, reliability and uptime, customer support, security and privacy and additional features according to <document, e.g. design, proposal, tender>; project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning). | proposed speed and bandwidth, availability and coverage, cost and package options, contract and fees, reliability and uptime, customer support, security and privacy and additional features according to <document, e.g. design, proposal, tender>; project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning).
|  | VAPT | General | Exclusion | Service | VAPT - Pre-Sales | Evaluating and accepting VAPT offer (including commercial negotiation)
|  | VAPT | General | Exclusion | Service | VAPT - Execution | Gathering necessary information required for performing VAPT, including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name> | , including but not limited to attending project meeting, collecting project documents from other parties, liaising with other parties, conducting feasibility study, attending any necessary off-site and / or on-site activity, as per requested by <customer project manager name>
|  | VAPT | General | Exclusion | Service | VAPT - Execution | Performing VAPT, including but not limited to providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work. | , including but not limited to providing detailed project plan, submitting UAT template for approval, liaising with site manager and other relevant parties regarding service activity arrangement, submitting required documents as per defined in <document, e.g. design, proposal, tender>, acquiring necessary document and approvals, such as Permit-To-Work.
|  | VAPT | General | Exclusion | Service | VAPT - Execution | Providing MoS, states aligned execution method and schedule, as well as the risks, control measures implementation method and contingency plan
|  | VAPT | General | Exclusion | Service | VAPT - Execution | Approving submitted VAPT MoS
|  | VAPT | General | Exclusion | Service | VAPT - Execution | Performing VAPT tasks according to approved MoS
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Submitting completion report template <e.g. UAT report>, indicates the work evaluation criteria for approval <e.g. proofing and demonstrating commissioned MGC functionalities : Real-time monitoring and control, Load balancing, Remote Access, Power Quality Monitoring, Automatic reconfiguration (fault occurrence), Energy Storage Operational Optimization, Predictive maintenance, Scalability, Grid integration, and Cybersecurity>
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Approving completion report template, as well as work evaluation criteria
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Arranging work evaluation activity (e.g. UAT)
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Attending work evaluation activity (e.g. UAT)
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Submitting completion report (including self or other party evaluation result, e.g. UAT with customer signature)
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Accepting completion report
|  | VAPT | General | Exclusion | Service | VAPT - Handover | Providing training (e.g. Operation, Troubleshooting, Emergency Response), if applicable
|  | VAPT | General | Exclusion | Service | VAPT - After-Sales | Drafting maintenance tasks (scheduled)
|  | VAPT | General | Exclusion | Service | VAPT - After-Sales | Drafting service level agreement (for ad-hoc service request)
|  | VAPT | General | Exclusion | Service | VAPT - After-Sales | Signing maintenance contract, and or service level agreement
|  | VAPT | General | Exclusion | Service | VAPT - After-Sales | Attending to ad-hoc service request
|  | VAPT | General | Exclusion | Service | VAPT - After-Sales | Attending to scheduled maintenance tasks

## Ref
Scope |  | Phase | Stakeholder
Inclusion |  | Initialization | LITEON
Exclusion |  | Proposal | Customer
Assumption / Customer Responsibility |  | Design | Panel maker
Microgrid Design - Pre-Sales
Microgrid Design - Execution
System |  | Microgrid Design - Handover
MGC | Microgrid Controller | Microgrid Design - After-Sales
CSMS | Charging Station Management System | DER Supplier - Pre-Sales | Assumption / Customer Responsibility
HEMS | Home Energy Management System | DER Supplier - Execution
PM |  | DER Supplier - Handover
General |  | DER Supplier - After-Sales
DER Installer - Pre-Sales
DER Installer - Execution
Category |  | DER Installer - Handover
Hardware |  | DER Installer - After-Sales
Software |  | DER Cabler - Pre-Sales
Service |  | DER Cabler - Execution
Process |  | DER Cabler - Handover
Data Acquisition |  | DER Cabler - After-Sales
DER Configurator - Pre-Sales
DER Configurator - Execution
DER Configurator - Handover
DER Configurator - After-Sales
ESS Supplier - Pre-Sales
ESS Supplier - Execution
ESS Supplier - Handover
ESS Supplier - After-Sales
ESS Installer - Pre-Sales
ESS Installer - Execution
ESS Installer - Handover
ESS Installer - After-Sales
ESS Cabler - Pre-Sales
ESS Cabler - Execution
ESS Cabler - Handover
ESS Cabler - After-Sales
ESS Configurator - Pre-Sales
ESS Configurator - Execution
ESS Configurator - Handover
ESS Configurator - After-Sales
Electrical DB Supplier - Pre-Sales
Electrical DB Supplier - Execution
Electrical DB Supplier - Handover
Electrical DB Supplier - After-Sales
Electrical DB Installer - Pre-Sales
Electrical DB Installer - Execution
Electrical DB Installer - Handover
Electrical DB Installer - After-Sales
Electrical DB Cabler - Pre-Sales
Electrical DB Cabler - Execution
Electrical DB Cabler - Handover
Electrical DB Cabler - After-Sales
Electrical DB Configurator - Pre-Sales
Electrical DB Configurator - Execution
Electrical DB Configurator - Handover
Electrical DB Configurator - After-Sales
LITEON HW Supplier - Pre-Sales
LITEON HW Supplier - Execution
LITEON HW Supplier - Handover
LITEON HW Supplier - After-Sales
LITEON HW Installer - Pre-Sales
LITEON HW Installer - Execution
LITEON HW Installer - Handover
LITEON HW Installer - After-Sales
LITEON HW Cabler - Pre-Sales
LITEON HW Cabler - Execution
LITEON HW Cabler - Handover
LITEON HW Cabler - After-Sales
LITEON HW Configurator - Pre-Sales
LITEON HW Configurator - Execution
LITEON HW Configurator - Handover
LITEON HW Configurator - After-Sales
EGCP Supplier - Pre-Sales
EGCP Supplier - Execution
EGCP Supplier - Handover
EGCP Supplier - After-Sales
EGCP Installer - Pre-Sales
EGCP Installer - Execution
EGCP Installer - Handover
EGCP Installer - After-Sales
EGCP Cabler - Pre-Sales
EGCP Cabler - Execution
EGCP Cabler - Handover
EGCP Cabler - After-Sales
EGCP Configurator - Pre-Sales
EGCP Configurator - Execution
EGCP Configurator - Handover
EGCP Configurator - After-Sales
EGCP Accessories Supplier - Pre-Sales
EGCP Accessories Supplier - Execution
EGCP Accessories Supplier - Handover
EGCP Accessories Supplier - After-Sales
EGCP Accessories Installer - Pre-Sales
EGCP Accessories Installer - Execution
EGCP Accessories Installer - Handover
EGCP Accessories Installer - After-Sales
EGCP Accessories Cabler - Pre-Sales
EGCP Accessories Cabler - Execution
EGCP Accessories Cabler - Handover
EGCP Accessories Cabler - After-Sales
EGCP Accessories Configurator - Pre-Sales
EGCP Accessories Configurator - Execution
EGCP Accessories Configurator - Handover
EGCP Accessories Configurator - After-Sales
MGC Integration and Commissioning - Pre-Sales
MGC Integration and Commissioning - Execution
MGC Integration and Commissioning - Handover
MGC Integration and Commissioning - After-Sales
Network Infrastructure Provider - Pre-Sales
Network Infrastructure Provider - Execution
Network Infrastructure Provider - Handover
Network Infrastructure Provider - After-Sales
Internet Service Provider - Pre-Sales
Internet Service Provider - Execution
Internet Service Provider - Handover
Internet Service Provider - After-Sales
VAPT - Pre-Sales
VAPT - Execution
VAPT - Handover
VAPT - After-Sales
Software supplier and deployer - Pre-Sales
Software supplier and deployer - Execution
Software supplier and deployer - Handover
Software supplier and deployer - After-Sales
Electrical DB
LITEON System
LITEON Hardware
Installation - 3rd party device, equipment
T and C - 3rd party device, equipment
Outsourcing
Procurement
Execution
Project Management
Control Panel
Accessories - Supply
Accessories - Installation
Accessories - T and C
Installation
Cabling
Internet
Development
Deployment
T and C
Integration
VAPT
Payment
Handover
After-Sales
After-Sales VAPT
O and M
Contingency

## MicrogridDesignDocs
Pre-sales : Proposal elements
Feasibility Study Report :
Documentation of the preliminary feasibility study conducted on the intended site, covering the solar irradiation, wind potential, energy consumption patterns, and integration with the utility grid.
Microgrid System Architecture :
A diagram describing the microgrid system's power routing, equipment placement, and network configuration.
Microgrid System Components :
A list of all components required for the microgrid systems, including technical data sheets, specifications, and certification details.
Conceptual Design Report :
A detailed report that outlines the conceptual design approach, outlining the proposed system's critical components, and detailing how each element controls and interacts with the others.
(Optional) Financial Models :
Documentation demonstrating the proposed system's economic feasibility, including payback time, levelized cost of energy, and lifetime costs.
Project References :
Reference from previous clients with highly-rated experiences working with the consultant or company proposing the system.
Execution
System Design Documents :
Detailed system architecture and design documents covering the microgrid concept, topology, energy generation, storage, distribution, and control systems.
Energy balance, demand forecasting, and modeling details that the design is based on.
Additionally, documentation specifying necessary service levels (reliability, availability, and efficiency), network layout designs.
Microgrid System Component Technical Specifications :
Detailed technical specifications of all components, equipment, and systems required for the microgrid. It should include product data sheets, specifications, certifications, and testing standards.
Control System Documentation :
Documentation for the microgrid control system. This should include control philosophy documents, control algorithms, and high level user interface design.
Integration Documentation :
Integration documentation for all microgrid equipment. This should include factory acceptance test results, test procedures, and report templates for each component, equipment, and systems.
Commissioning and Acceptance Test Plans :
Plans for commissioning and acceptance tests at various stages of the project lifecycle, including the commissioning plan, factory acceptance tests, site acceptance tests, and performance qualification tests.
Operations and Maintenance Documentation :
Technical Manuals for all equipment and systems. This should encompass requirements and methods for testing, servicing, repairing, and replacing to ensure that the system operations and maintenance is efficient.
Project Plan :
An outline of the intended design process, key deliverable dates, and milestone-based project completion.
Cybersecurity Documentation :
Cybersecurity guidelines to ensure the protection and security of all assets, systems, and data associated with the microgrid.
Warranties and Life Cycle costs :
Any warranties, system guarantees, and life-cycle costs for each component, solenoid system, equipment, and systems used in the microgrid.

## NetworkInfra
A network infrastructure proposal should generally include the following elements:
Pre-sales : Proposal elements
Client requirements :
A summary of the client's needs and goals for their network infrastructure.
Scope of work :
A description of the work to be performed, including details on installation, configuration, testing, and deployment of the network infrastructure.
Network design :
A detailed explanation of the proposed network infrastructure design, including topology, network protocols, hardware, and software components, and how they will support the client's requirements.
Hardware and software components :
A list of the hardware and software required for the network infrastructure, including switches, routers, servers, firewalls, and other necessary equipment.
Security and redundancy :
A description of the security measures and redundancy protocols incorporated in the network design, including firewalls, data encryption, backup and failover systems, and disaster recovery procedures.
Implementation plan :
A timeline detailing the phases of implementation, along with associated milestones, testing, and quality assurance processes.
Cost breakdown :
A detailed breakdown of the costs associated with equipment, software, labor, and other expenses.
Service level agreements :
An outline of the support services to be provided after deployment, including ongoing maintenance, monitoring, and service level agreements.
Risks and assumptions :
A description of the assumptions made in the design and the associated risks to the project's success.
Conclusion and recommendations :
A summary of the proposal along with any recommendations and additional details that would help the client make an informed decision on the project.

## InternetService
When requesting internet service from an ISP (Internet Service Provider), here are some factors that you may want to consider:
Speed and bandwidth :
Determine the minimum speed and bandwidth that meets your needs based on the number of devices and users in your home or business.
Availability and coverage :
Check if the ISP provides coverage in your area and if the type of internet connection suits your needs.
Cost and package options :
Compare different package options and costs from different ISPs to find the most suitable plan that meets your budget.
Contract and fees :
Consider the contract length, termination fees, and installation charges.
Reliability and uptime :
Check the ISP's history of reliability and uptime. Look for reviews and ratings from customers.
Customer support :
Check the ISP's customer service and technical support availability, quality, and satisfaction.
Security and privacy :
Evaluate the ISP's policies and measures in securing and protecting user privacy and data.
Additional features :
Check if the ISP offers additional features such as email, cloud storage, or parental control.
proposed speed and bandwidth, availability and coverage, cost and package options, contract and fees, reliability and uptime, customer support, security and privacy and additional features according to <document, e.g. design, proposal, tender>; project management (including resource management, labour work permit application, labour safety certificate (e.g. CSOC, BCSS) acquisition, labour professional qualification (e.g. LEW, PE) acquisition, project planning).

## VAPT
VAPT proposal elements
Pre-sales : Proposal elements
x |  | Introduction :
An introduction to the organization that is seeking VAPT services, including information about the company, its size, and its industry.
x |  | Objectives :
A summary of the objectives for the VAPT assessment, including the scope of the review, the type of vulnerabilities to be evaluated, and the anticipated outcomes.
x |  | Evaluation Criteria :
The criteria that will be used to evaluate vendor proposals, including qualifications, experience, method of a proposal, and pricing.
v |  | Qualifications :
A description of the qualifications of the VAPT vendor, including their experience, technical qualifications, and certifications.
v |  | Scope of Work :
A detailed description of the work to be performed, including vulnerability scanning, penetration testing, social engineering testing, and other relevant assessments. Additionally, it should describe the expected scope of the assessment, such as the number of systems and applications to be tested.
v |  | Technical Requirements :
Technical requirements related to the VAPT, such as hardware and software requirements for the assessment.
v |  | Methodology :
A detailed explanation of the VAPT methodology to be used by the vendor, including the tools and techniques to be used during the assessment.
v |  | Deliverables :
A list of the expected deliverables, including a detailed report outlining the vulnerabilities discovered, recommendations for mitigation, and an executive summary.
v |  | Work Plan :
A detailed work plan outlining the phases of the assessment, along with associated milestones and timelines.
v |  | Contract Terms :
The terms and conditions of the contract, including the start date, the duration of the assessment, payment terms, and any associated penalties or fees.
Execution
x |  | Reporting :
A description of the reporting process, including how results will be reported, the format of the report, and the timeline for reporting.
Some of the most commonly used standards for VAPT are:
OWASP Testing Guide: This is a comprehensive guide that provides methodologies and tools to conduct VAPT assessments of web applications.
NIST SP 800-53: This is a security standard published by the National Institute of Standards and Technology (NIST) that provides guidelines for federal agencies regarding security and privacy controls.
ISO/IEC 27001: This is an information security management standard that provides guidelines for establishing, implementing, monitoring, and improving an organization's information security management system.
PCI DSS: This is a payment card industry standard that provides guidelines for securing payment card data.
OSSTMM: This is a penetration testing methodology that provides a comprehensive framework for conducting ethical hacking and penetration testing.

## (obs)workflow
Network analysis and feasibility study report | This report should include a comprehensive analysis of the existing electricity infrastructure, including detailed load calculations and a study of the renewable energy resources available at the site to determine if implementing a microgrid is feasible.
Specification and cost estimate for equipment and software | You should request from potential vendors a detailed list of all necessary hardware, software, and networks required to build and run the microgrid.
Detailed Project Plan | This will detail all the tasks and steps required to complete the project, including the timeline, dependencies and any deliverables.
Technical and Commercial Proposal | You should request a proposal from potential vendors specifying their technical solution and commercial terms for supplying and integrating the required equipment and software.
Draft Technical and Commercial Contract | Request a preliminary contract for the supply and integration of equipment and software, specifying the scope, timelines, payment milestones, warranties, dispute resolution mechanisms and any other required terms and conditions.
Reference list and Case Studies | You should ask for a list of references and case studies from each potential vendor. These documents can provide insights into prior experiences, insights, and successes with similar projects.
Warranty Details | Request details related to warranties on hardware, software, and service for the microgrid project.
SLA Details | Ask for the details of Service Level Agreements (SLAs) that match the equipment and services offered by vendors.
Demo and Proof of Concept | You could request a demo or proof of concept of the equipment or software to check the functionality and compatibility with the provided requirements.
1. Planning and Feasibility Assessment:=> Network analysis and feasibility study report
Initial site survey => Site survey report ()
Analyze the existing electrical infrastructure
Study and assess the load demands
Incorporate an energy audit to identify energy conservation opportunities
Check renewable energy resources available at the site
Identify potential integration issues
Financial analysis and evaluation
2. Design and Engineering:
Develop a microgrid layout and testing activities
Develop electrical and mechanical design plans
Developing Drawings and schematics
Specify equipment and select vendors
Develop Control Systems and Network Integration
Testing and Certification
3. Construction and Commissioning:
Site preparation
Procurement and delivery of equipment
Installation of equipment
Commissioning and testing of equipment
Integration Testing and commissioning
Complete system testing
4. Operation and maintenance:
Ongoing performance monitoring
Maintenance schedule
Repairs and replacements of damaged equipment
Continuous system monitoring
Upgrade and modifications for better performance
Operator training
Emergency Response Plan scheduling and implementation.
Planning and Feasibility Assessment