## Gantt Chart Template
Project Name |  | NTU WP4 |  |  |  |  | has formula
Latest update |  | 09-Jun-2023, Gabriel |  | Day 0 : |  |  | 2021-10-01
Marketing Plan Gantt Chart Template
Show | WBS No. | Name | ¦ | Progress |  |  | Start* | Due* | Start on Day* | Duration* | Dependency | Responsible | Accountable | Consulted | Informed | Risk | Control | ¦ | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
> |  | M0. Kick off - Benchmarking and project requirement analysis | ¦ | 100% | 0 | 4 | 2021-10-01 | 2023-06-17 | 0 | 624 | [7 empty] | ¦
> |  | Benchmark Report (Planned) | ¦ |  |  |  | 2021-10-01 | 2022-12-29 | 0 | 455 | [7 empty] | ¦
> |  | Benchmark Report (Actual) | ¦ | 100% |  |  | 2021-10-01 | 2022-01-20 | 0 | 112 | [7 empty] | ¦
> |  | LITEON Validation And Acceptance | ¦ | 100% |  |  | 2023-06-13 | 2023-06-17 | 620 | 5 | [7 empty] | ¦
|  |  | ¦ | [14 empty] | ¦
> |  | M1. Functional Requirement Specification (Project Requirement Document) | ¦ | 100% |  |  | 2023-06-12 | 2023-06-24 | -44470 | 12 | [7 empty] | ¦
> |  | PRD V1.0, covers : M5, M8, M9, M10, M11, M12, M13 | ¦ | 100% | 5 | 11 | 2023-06-17 | 2023-06-23 | 624 | 7 | [7 empty] | ¦
> |  | LITEON Validation And Acceptance | ¦ | 100% |  |  | 2023-06-12 | 2023-06-12 | 619 | 1 | [7 empty] | ¦
> |  | PRD V2.0, covers : M14, M15, M16 | ¦ | 100% | 10 | 12 | 2023-06-22 | 2023-06-24 | 629 | 3 | [7 empty] | ¦
> |  | LITEON Validation And Acceptance | ¦ | [5 empty] | -44470 | 1 | [7 empty] | ¦
|  |  | ¦ | [14 empty] | ¦
> |  | Scheduling: | ¦ | 100% |  |  | 2023-06-12 | 2023-07-02 | 619 | 20 | [7 empty] | ¦
|  | Schedule new articles | ¦ | 100% | 15 | 18 | 2023-06-27 | 2023-06-30 | 634 | 4 | [7 empty] | ¦
|  | Publish new articles | ¦ | 100% | 16 | 20 | 2023-06-28 | 2023-07-02 | 635 | 5 | [7 empty] | ¦
|  |  | ¦ |  |  |  | 2023-06-12 | 2023-06-12 | 619 | 1 | [7 empty] | ¦
|  |  | ¦ |  |  |  | 2023-06-12 | 2023-06-12 | 619 | 1 | [7 empty] | ¦
|  |  | ¦ |  |  |  | 2023-06-12 | 2023-06-12 | 619 | 1 | [7 empty] | ¦
|  |  | ¦ | [14 empty] | ¦
> |  | Newsletter: | ¦ | 100% |  |  | 2023-07-05 | 2023-07-20 | 642 | 15 | [7 empty] | ¦
|  | Choose topics | ¦ | 100% | 23 | 33 | 2023-07-05 | 2023-07-15 | 642 | 11 |  | Mark | [5 empty] | ¦
|  | Design layout | ¦ | 100% | 23 | 33 | 2023-07-05 | 2023-07-15 | 642 | 11 |  | Wendy | [5 empty] | ¦
|  | Write content | ¦ | 100% | 24 | 34 | 2023-07-06 | 2023-07-16 | 643 | 11 |  | Alice | [5 empty] | ¦
|  | Select publishing date | ¦ | 100% | 25 | 34 | 2023-07-07 | 2023-07-16 | 644 | 10 |  | John | [5 empty] | ¦
|  | Publish | ¦ | 100% | 25 | 38 | 2023-07-07 | 2023-07-20 | 644 | 14 |  | Mark | [5 empty] | ¦
|  |  | ¦ | [14 empty] | ¦
> |  | Press Release: | ¦ | 71.67% |  |  | 2023-07-12 | 2023-07-22 | 649 | 10 | [7 empty] | ¦
|  | Select media outlet | ¦ | 100% | 30 | 38 | 2023-07-12 | 2023-07-20 | 649 | 9 |  | Mark | [5 empty] | ¦
|  | Prepare content | ¦ | 80% | 30 | 38 | 2023-07-12 | 2023-07-20 | 649 | 9 |  | John | [5 empty] | ¦
|  | Prepare design | ¦ | 50% | 30 | 38 | 2023-07-12 | 2023-07-20 | 649 | 9 |  | Alice | [5 empty] | ¦
|  | Call media outlet | ¦ | 100% | 33 | 39 | 2023-07-15 | 2023-07-21 | 652 | 7 |  | Alice | [5 empty] | ¦
|  | Write press release | ¦ | 100% | 33 | 39 | 2023-07-15 | 2023-07-21 | 652 | 7 |  | John | [5 empty] | ¦
|  | Send to editor | ¦ | 0% | 34 | 40 | 2023-07-16 | 2023-07-22 | 653 | 7 |  | Mike | [5 empty] | ¦
|  |  | ¦ | [14 empty] | ¦
> |  | New web page: | ¦ | 84.29% |  |  | 2023-07-18 | 2023-07-30 | 655 | 12 | [7 empty] | ¦
|  | Define look & feel | ¦ | 100% | 36 | 42 | 2023-07-18 | 2023-07-24 | 655 | 7 |  | Alice | [5 empty] | ¦
|  | Write sections | ¦ | 100% | 37 | 42 | 2023-07-19 | 2023-07-24 | 656 | 6 |  | Wendy | [5 empty] | ¦
|  | Approve sections | ¦ | 100% | 38 | 42 | 2023-07-20 | 2023-07-24 | 657 | 5 |  | Mark | [5 empty] | ¦
|  | UX/UI | ¦ | 100% | 38 | 45 | 2023-07-20 | 2023-07-27 | 657 | 8 |  | John | [5 empty] | ¦
|  | Write content | ¦ | 100% | 40 | 46 | 2023-07-22 | 2023-07-28 | 659 | 7 |  | Wendy | [5 empty] | ¦
|  | Approve design | ¦ | 40% | 40 | 48 | 2023-07-22 | 2023-07-30 | 659 | 9 |  | Alice | [5 empty] | ¦
|  | Share with team | ¦ | 50% | 40 | 50 | 2023-07-22 | 2023-08-01 | 659 | 11 |  | Mark | [5 empty] | ¦
|  |  | ¦ | [14 empty] | ¦
Formulas:
Start* = MIN([Start*, row below]:H9)
Due* = MAX([Due*, row below]:I9)
Duration* = DATEDIF([Start*],[Due*],"d")+1
Note on C5: Gabriel Chen: * Conducting Platform Benchmarking Analysis, Green Nudges frameworks, Data standards, Gateways and Sensor recommendations * Note : This has to be quantitatively differentiated atleast by end of 1st year after completion of tests by NTU team.
Note on C10: Gabriel Chen: * Note : A PRD document stating the contents agreeable by both parties to cover all the functional aspects of Data fusion core platform and its architecture, smart home fusion use case, smart grid fusion use cases, supported protocols, UI requirements, deliverables in detail.

## Manual Chart Gantt Template
|  | Build Gantt Charts Easily with Instagantt. Just click here. | [24 empty] | Marketing Plan Gantt Chart Template
Level | Name | Progress | Start | Due | User | Completion Date | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk | Duration (Cal. Days) | 01/07/2019 | 01/08/2019 | 01/09/2019 | 01/10/2019 | 01/11/2019 | 01/12/2019 | 01/13/2019 | 01/14/2019 | 01/15/2019 | 01/16/2019 | 01/17/2019 | 01/18/2019 | 01/19/2019 | 01/20/2019 | 01/21/2019 | 01/22/2019 | 01/23/2019 | 01/24/2019 | 01/25/2019 | 01/26/2019 | 01/27/2019 | 01/28/2019 | 01/29/2019 | 01/30/2019 | 01/31/2019 | 02/01/2019 | 02/02/2019 | 02/03/2019 | 02/04/2019 | 02/05/2019 | 02/06/2019 | 02/07/2019 | 02/08/2019 | 02/09/2019 | 02/10/2019 | 02/11/2019 | 02/12/2019 | 02/13/2019 | 02/14/2019 | 02/15/2019 | 02/16/2019 | 02/17/2019 | 02/18/2019 | 02/19/2019 | 02/20/2019 | 02/21/2019 | 02/22/2019 | 02/23/2019 | 02/24/2019 | 02/25/2019 | 02/26/2019 | 02/27/2019 | 02/28/2019 | 03/01/2019 | 03/02/2019 | 03/03/2019 | 03/04/2019 | 03/05/2019 | 03/06/2019 | 03/07/2019 | 03/08/2019 | 03/09/2019 | 03/10/2019 | 03/11/2019 | 03/12/2019 | 03/13/2019 | 03/14/2019 | 03/15/2019 | 03/16/2019 | 03/17/2019 | 03/18/2019 | 03/19/2019 | 03/20/2019 | 03/21/2019 | 03/22/2019 | 03/23/2019 | 03/24/2019 | 03/25/2019 | 03/26/2019 | 03/27/2019 | 03/28/2019 | 03/29/2019 | 03/30/2019 | 03/31/2019 | 04/01/2019 | 04/02/2019 | 04/03/2019
1 | Brainstorming session: | 50% |  |  | Mark |  | 25 | 28 |  |  | 5 | 4 | 5
1 | Schedule tasks | 90% | 01/07/2019 | 01/11/2019 | John |  | 15 | 20 |  |  | 5 | 4 | 5
1 | Assign content ideas | 100% | 01/10/2019 | 01/11/2019 | Alice |  | 10 | 8 |  |  | 5 |  | 2
1 | Blog Design: | 100% |  |  |  |  | 95 | 84 | 1600 | 1550 | 4 | 2 | 12
1 | Define new look for blog | 100% | 01/14/2019 | 01/25/2019 | Mark |  | 2 | 2 |  |  | 4 | 2 | 12
1 | Begin design process | 100% | 01/15/2019 | 01/25/2019 | Alice |  | 48 | 40 | 500 | 450 | 3 | 2 | 11
1 | Define new CTAs | 100% | 01/21/2019 | 01/25/2019 | John |  | 45 | 42 | 300 | 325 | 2 | 1 | 5
1 | Launch blog | 100% | 01/25/2019 | 01/25/2019 | Mike |  |  |  | 800 | 775 | 5 | 2 | 1
1 | Scheduling: | 100% |  |  |  |  | 112 | 98 | 350 | 250 | 4 | 3 | 5
1 | Schedule new articles | 100% | 01/28/2019 | 02/01/2019 | Mark |  | 72 | 72 | 350 | 250 | 5 | 5 | 5
1 | Publish new articles | 100% | 01/30/2019 | 02/01/2019 | Alice |  | 36 | 24 |  |  | 3 | 3 | 3
1 | Assign new topics to writers | 100% | 02/01/2019 | 02/01/2019 | John |  | 4 | 2 |  |  | 5 | 1 | 1
1 | Newsletter: | 95% |  |  |  |  | 28 | 28 |  |  | 4 |  | 11
1 | Choose topics | 100% | 01/14/2019 | 01/18/2019 | Mark |  | 5 | 4 |  |  | 5 |  | 5
1 | Design layout | 100% | 01/16/2019 | 01/18/2019 | Wendy |  | 10 | 10 |  |  | 5 |  | 3
1 | Write content | 100% | 01/21/2019 | 01/23/2019 | Alice |  | 10 | 12 |  |  | 5 |  | 3
1 | Select publishing date | 100% | 01/21/2019 | 01/21/2019 | John |  | 1 | 0.5 |  |  | 2 |  | 1
1 | Publish | 100% | 01/24/2019 | 01/24/2019 | Mark |  | 1 | 1 |  |  | 5 |  | 1
1 | Share on Social Media | 70% | 01/24/2019 | 01/24/2019 | Mike |  | 1 | 0.5 |  |  | 3 |  | 1
1 | Press Release: | 61% |  |  |  |  | 53 | 50 | 855 | 655 | 4 | 3 | 15
1 | Select media outlet | 100% | 02/11/2019 | 02/12/2019 | Mark |  | 10 | 9 | 200 | 150 | 5 | 3 | 2
1 | Prepare content | 80% | 02/11/2019 | 02/15/2019 | John |  | 15 | 10 | 450 | 300 | 4 | 1 | 5
1 | Prepare design | 50% | 02/13/2019 | 02/15/2019 | Alice |  | 20 | 24 | 100 | 100 | 3 |  | 3
1 | Call media outlet | 100% | 02/18/2019 | 02/18/2019 | Alice |  | 1 | 1 |  |  |  |  | 1
1 | Write press release | 100% | 02/18/2019 | 02/21/2019 | John |  | 5 | 4 | 105 | 105 | 5 | 4 | 4
1 | Send to editor | 0% | 02/25/2019 | 02/25/2019 | Mike |  | 1 | 1 |  |  |  |  | 1
1 | Send press release | 0% | 02/25/2019 | 02/25/2019 | Mark |  | 1 | 1 |  |  |  |  | 1
1 | New web page: | 100% |  |  |  |  | 9.5 | 9.5 | 100 | 150 | 4 | 3 | 12
1 | Define look & feel | 100% | 02/18/2019 | 02/22/2019 | Alice |  | 3 | 3 | 100 | 150 | 4 | 3 | 5
1 | Write sections | 100% | 02/21/2019 | 02/21/2019 | Wendy |  | 1 | 1 |  |  |  |  | 1
1 | Approve sections | 100% | 02/21/2019 | 02/21/2019 | Mark |  | 1 | 1 |  |  | 4 | 4 | 1
1 | UX/UI | 100% | 02/26/2019 | 02/26/2019 | John |  | 1 | 1 |  |  |  |  | 1
1 | Write content | 100% | 02/20/2019 | 02/20/2019 | Wendy |  | 0.5 | 0.5 |  |  | 4 | 1 | 1
1 | Approve design | 100% | 03/01/2019 | 03/01/2019 | Alice |  | 3 | 3 |  |  |  |  | 1
1 | Share with team | 53% | 03/16/2019 | 03/16/2019 | Mark |  | 22 | 3 | 400 | 450 | 5 | 1 | 27
1 | Launch new web | 100% | 02/11/2019 | 02/22/2019 | Jason |  | 4 | 3 | 150 | 200 | 5 | 2 | 12
1 | New content | 40% | 02/18/2019 | 02/22/2019 | Victor Pascow |  | 15 |  | 250 | 250 | 5 | 1 | 5
1 | Choose topics | 50% | 02/22/2019 | 02/22/2019 | Wendy Torrance |  | 2 | [5 empty] | 1
1 | Design layout | 75% | 03/04/2019 | 03/04/2019 | Andy Barclay |  | 1 |  |  |  | 5 | 1 | 6
1 | Write content | 0% | 03/04/2019 | 03/04/2019 | Laurie Strode | [7 empty] | 1
1 | Select publishing date | 67% | 02/25/2019 | 03/11/2019 |  |  | 16 | 20 | 425 | 403 | 5 | 2 | 15
1 | Publish | 100% | 02/25/2019 | 02/27/2019 | Alice |  | 5 | 4 | 50 | 50 | 5 | 3 | 3
1 | Share on Social Media | 100% | 02/27/2019 | 03/05/2019 | Mark |  | 10 | 15 | 200 | 178 | 5 | 2 | 7
1 | Newsletter: | 100% | 03/04/2019 | 03/04/2019 | John |  | 1 | 1 |  |  | 4 | 1 | 1
1 | Choose topics | 100% | 02/28/2019 | 03/08/2019 | Wendy |  |  |  | 75 | 75 |  |  | 9
1 | Design layout | 0% | 03/11/2019 | 03/11/2019 | Jason |  |  |  | 100 | 100 | 4 | 1 | 1
1 | Write content | 0% | 03/11/2019 | 03/11/2019 | Mark | [7 empty] | 1
1 | Select publishing date | 49% |  |  |  |  | 120 |  | 600 |  | 4 | 3 | 24
1 | Publish | 100% | 03/11/2019 | 03/15/2019 | Alice |  | 72 |  |  |  | 5 | 1 | 5
1 | New brainstorming session: | 100% | 03/15/2019 | 03/15/2019 | Wendy |  | 1 | [5 empty] | 1
1 | Schedule session | 100% | 03/15/2019 | 03/15/2019 | Mark |  | 4 | [5 empty] | 1
1 | Write ideas | 40% | 03/18/2019 | 03/22/2019 | John |  | 25 |  | 300 |  | 5 | 4 | 5
1 | Assign content ideas | 50% | 03/19/2019 | 03/22/2019 | Wendy |  | 10 |  | 250 |  | 3 | 2 | 4
1 | Write content | 0% | 03/18/2019 | 03/22/2019 | Alice |  | 2 |  |  |  | 5 | 3 | 5
1 | Define dates | 0% | 03/26/2019 | 03/26/2019 | Mark |  | 1 |  |  |  | 3 |  | 1
1 | Review contents | 0% | 04/01/2019 | 04/03/2019 | Jason |  | 5 |  | 50 |  | 5 | 4 | 3

## Ref
Source : https://instagantt.com/free-gantt-chart-template-for-excel?gclid=Cj0KCQjw4NujBhC5ARIsAF4Iv6dROTDd33KbG6PzK0K9DU-LM9pwlVgDX5uekjKwTQZ2_9AaNZKFkeAaAhBIEALw_wcB
Collect date | (01-Jun-2023)