## Sheet1
| Phase | Document | Category | Format | Recommended priority (current situation) | Progress
1 | Pre-Sales > Technical Feasibility Study | Compliance table | Project basis | XLSX | Low
| Pre-Sales > Technical Feasibility Study | Site survey report | Project basis | DOCX or PPTX | Low
| Pre-Sales > Technical Feasibility Study | Pilot / Trial test report | Project basis | PPTX or DOCX | Low
2 | Pre-Sales > Technical Proposal | Architecture Diagram | Product | Drawing | Low
| Pre-Sales > Technical Proposal | Network connection diagram | Project basis | Drawing | Low
| Pre-Sales > Technical Proposal | Layout Diagram | Project basis | Drawing | Low
| Pre-Sales > Technical Proposal | Wiring Diagram | Project basis | Drawing | Low
| Pre-Sales > Technical Proposal | BOM / BOQ (hardware + software + services) | Project basis | XLSX | Medium | (07-Jun-2023) 100%, template obtained and used for PT Astra project
| Pre-Sales > Technical Proposal | Scope of Work (Inclusion) | Project basis | DOCX | Medium | (07-Jun-2023) 100%, drafted for PT Astra project
| Pre-Sales > Technical Proposal | Scope of Work (Exclusion) | Project basis | DOCX | Medium | (07-Jun-2023) 100%, drafted for PT Astra project
| Pre-Sales > Technical Proposal | Customer Responsibility | Project basis | DOCX | Medium | (07-Jun-2023) 100%, drafted for PT Astra project
| Pre-Sales > Technical Proposal | High-level Project Plan | Project basis | XLSX | Medium | (07-Jun-2023) 100%, drafted for PT Astra project and others
| Pre-Sales > Technical Proposal | Project Org-Chart | Project basis | Drawing | Low | (21-Jun-2023) 100% (+100%), drafted for PT Astra project
| Pre-Sales > Technical Proposal | Product Certificates | Product | DOCX | Low
3 | Project Execution > Qualifications & Permission | Team members' safety certificates | General | DOCX or XLSX | Medium | (07-Jun-2023) 0%, May not be applicable for software project
| Project Execution > Qualifications & Permission | Permit To Work / License | Project basis | DOCX or XLSX | Low
| Project Execution > Qualifications & Permission | SIC, Site Introduction Course Attendance List | Project basis | XLSX | Low
| Project Execution > Qualifications & Permission | Toolbox Meeting Template | Project basis | DOCX or XLSX | Low
| Project Execution > Qualifications & Permission | Risk Assessment | Project basis | DOCX or XLSX | Medium | (07-Jun-2023) 5%, gathering inputs and subject to project requirement
4 | Project Execution > Way of Working | RACI Matrix | Project basis | XLSX | Medium | (07-Jun-2023) 25%, requires further internal discussion for project specific tasks
| Project Execution > Way of Working | Varies Process Workflows | Project basis | Drawing | High | (07-Jun-2023) 75%, 10 workflows for PT Astra were drafted
| Project Execution > Way of Working | Project Gantt-Chart | Project basis | XLSX | High | (21-Jun-2023) 95% (+5%), drafted for PT Astra project and others, also searching for better template (07-Jun-2023) 90%, drafted for PT Astra project and others, also searching for better template
5 | Project Execution > Deliverables | Requirements Specification Document | Project basis | DOCX or PPTX or Drawing or popular UI design tools' file such as Figma, Zeplin | High | (21-Jun-2023) 45% (+40%), identified template to be used, drafted for Mobile App UI. Next step is for WebUI > Processes (07-Jun-2023) 5%, identifing the template to be used
| Project Execution > Deliverables | Project Intake Form | Project basis | XLSX | Low
| Project Execution > Deliverables | UAT Report Template | Project basis | DOCX or XLSX or PPTX | High | (07-Jun-2023) 25%, template available, content to be filled
6 | Project Execution > Development | Development MoS (Method of Statement) | Project basis | DOCX or XLSX | Low
| Project Execution > Development | Software Design Document | Project basis | DOCX or Drawing | Low
7 | Project Execution > Deployment | Deployment MoS | Project basis | DOCX or Drawing | Medium | (07-Jun-2023) 5%, template available
8 | Project Execution > Reporting | Progress Meeting Minutes | Project basis | DOCX | Medium | (07-Jun-2023) 5%, template available
9 | Project Execution > Installation | Installation Manual (Hardware + Software) | Product | DOCX | Low
10 | Project Execution > Testing And Commissioning | Configuration Guide, Testing And Commissioning Manual | Product | DOCX or PPTX | Low
11 | Project Execution > Integration | Integration MoS | Project basis | DOCX or PPTX | Medium | (07-Jun-2023) 5%, template available
12 | Handover > Training | User Operation Manual | Product | PPTX or DOCX | Medium | (07-Jun-2023) 20%, CSMS has UM for Web UI but not Mobile UI; Other segments has none
| Handover > Training | Troubleshooting Guide | Product | PPTX or DOCX | Medium | (07-Jun-2023) 5%, template available
| Handover > Training | Training Attendance List | Project basis | XLSX | Low
13 | After-Sales > Ad-hoc Services | Service Report | General | DOCX or XLSX | Medium | (07-Jun-2023) 5%, template available, revisions required
14 | After-Sales > End Of DLP | Certificate of Final Completion | Project basis | DOCX | Medium | (07-Jun-2023) 5%, template available
15 | After-Sales > Change Request | Change request | General | DOCX | Medium | (07-Jun-2023) 5%, template available
16 | After-Sales > Maintenance | Maintenance report | General | DOCX or XLSX | Low